## SCORECARD
Khalifa University of Science and Technology
2020-2022 BALANCED SCORECARD and PERFORMANCE REPORT
PERSPECTIVE | Strategic Objective/ Operational Objective | KU Objective | RC Objective | KPIs | Frequency | Unit | Actual | Target |  |  |  |  | Actual
[7 empty] | 2020 | 2021 |  |  |  | 2021 | 2021 |  |  |  | 2020
[8 empty] | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
Students and Community | Strategic Objective | Develop and implement a research strategy that addresses the national and international priorities | Develop Research Computing strategy | Develop and implement RC strategy | Annual | Strategy document | Strategy Drafted | Final document |  |  |  | Complete strategy document and start implementation
|  |  | Research Computing Survey | d | Annual | Report of analysis | Not reported for 2020, survey released January 2021 | Distribute and complete analysis |  |  |  | Complete analysis and incorporate findings into strategy
|  |  | Reseach Computing Committee (meetings) | Regular meetings | Annual | Documents and Number of meetings | Charter approved, committee established and held two meetings | Hold first meeting | 2nd meeting | 3rd meeting | 4th meeting | Minimum 4 meetings. Meeting minutes to be documented and actions taken.
|  |  | Reseach Support and Data Intelligence Center(RDISC) Computational resources | Define and coordinate procurement of computational resources | Annual | Computational resources | New initiative | Define computational requirements | Release RFP for equipment | Award RFP | Receive and coordinate coniguration of computational resources | Procurement of resources, and configuration.
Internal | Operational Objective | Utilize state-of-the-art technologies and facilities in an optimal and efficient manner | HPC platform and other RC resources | % utilization rate of RC resources | Annual | Percentage | Average utilization: 70% | Configure new HPC cluster, and launch Pilot service | Launch HPC cluster and put into production |  |  | Average utilization: 80%
|  |  |  | % unplanned downtime | Annual | Percentage | Percentage uptime: 95% |  |  |  |  | Percentage uptime: 90%
|  |  |  | Training Portfolio | Annual | Number | 5 training courses |  | Develop new training course | Develop new training course |  | 7 training courses in portfolio
|  |  |  | Training courses delivered | Annual | Number | 72 courses delivered | Deliver 10 training courses | Deliver 10 training courses | Deliver 10 training courses | Deliver 10 training courses | Deliver 40 training courses
|  |  |  | Number of users trained | Annual | Number | 267 users trained | 50 users trained | 50 users trained | 50 users trained | 50 users trained | 200 users trained
| Operational Objective | Enhance the communication plan and outreach activities | User Base engagement | Organise outreach Events | Quarterly | No. of events | 1 User engagement event held (online) |  |  |  | Organise outreach event | 1 outreach event
|  |  |  | Establish User Group and hold regular meetings | Quarterly | No. of meetings | 1 User Group Meeting held (online) |  | Organise 1st User Group Meeting | Organise 2nd User Group Meeting | Ogranise 3rd User Group Meeting | 3 User group Meetings
| Operational Objective | Ensure the university sustainability | Equipment lifecycle mangement | Report on equipment management | Annual |  | All equipment at end of useful life |  |  |  |  | Report of status of all RC resources
| Operational Objective | Provide reliable, accurate and timely reports to different stakeholders | Automate and publish utlilization rates | Availabiity of publised utilization rates | Annual | Generally available statistics | Statistical reporting tools developed |  | Updating tools due to new Cluster | Pilot tools for utlization | Make tools generally available | Make utilization rates geneally accessible
|  |  | Regular Monthly reports | Delivery of monthly reports | Annual | Number | 12 reports | 3 reports | 3 reports | 3 reports | 3 reports | 12 reports
| Operational Objective | Develop a process framework for the university operations | Processes for Department | Create and document processes for user management | Annual | Appropriate processes | Process developed and documented |  | Update and implment process for user Management | Get processes approved by RCC and SVP |  | Updated process for User management Processes to be approved by RCC and SVP of R&D
|  |  |  | Create and document processes for resource management | Annual | Appropriate processes | One Processes developed and documented |  |  | Complete process for 2 services | Get processes approved by RCC and SVP | Updated process for each service run by RC
Learning and Growth | Strategic Objective | Design and implement professional development programs for researchers, faculty ans staff to contribute to the university strategic plan | Training plan for all department staff | All staff should attend at least one training course a year | Annual | Number of staff trained | 2 Staff attended online training |  |  |  |  | 4

## For monthly report
RC Objective | KPIs | Q1 target | Q2 target | Q3 target | Q4 target | Q3 Target | Status
Develop Research Computing strategy | Develop and implement RC strategy | Final Document |  |  |  |  | New document drafted and presented to RCC in April 2021. Further work is needed to incorporate comments from SVP. .
Research Computing Survey | Report and analysis of responses to be used in developing RC strategy | Distribute and complete analysis |  |  |  |  | Survey and analysis completed.
Establish Reseach Computing Committee (Charter and meetings) | Charter and regular meetings | 1st meeting | 2nd meeting | 3rd meeting |  | 3rd meeting | 2nd meeting to be scheduled in Q3
Reseach Support and Data Intelligence Center(RDISC) Computational resources | Define and coordinate procurement of computational resources | Define computational requirements | Release RFP for equipment | Award RFP | Receive and coordinate coniguration of computational resources | Award RFP | Documents submitted and with Procurement department
HPC platform and other RC resources | % utilization rate of RC resources | Configure new HPC cluster, and launch Pilot service | Launch HPC cluster and put into production |  |  |  | Pilot service launched, and production service to be launched in August Masdar and SAN based resources decomssioned
| % unplanned downtime | 0% | 0% |  |  |  | Percentage uptime: 90%
| Training Portfolio |  | Develop new training course | Develop new training course |  | Develop new training course | 5 training courses in portfolio, which have all been updated to include new content for new HPC cluster
| Training courses delivered | Deliver 10 training courses | Deliver 10 training courses | Deliver 10 training courses | Deliver 10 training courses | Deliver 10 training courses | Delivered 10 training courses in Q1
| Number of users trained | 50 users trained | 50 users trained | 50 users trained | 50 users trained | 50 users trained | To date, 57 users trained in Q1. 88 users trained in Q2, mainly with the Introduction to the new cluster, Al Mesbar.
User Base engagement | Organise outreach Events |  |  |  | Organise outreach event
| Establish User Group and hold regular meetings |  | Organise 1st User Group Meeting | Organise 2nd User Group Meeting | Ogranise 3rd User Group Meeting | Organise 2nd User Group Meeting | Planning for first meeting to coincide with launch of new HPC.
Equipment lifecycle mangement | Report on equipment management | [5 empty] | Aspects will be incorporated into strategy document
Automate and publish utlilization rates | Availabiity of publised utilization rates |  | Updating tools due to new Cluster | Pilot tools for utlization | Make tools generally available | Pilot tools for utliization | Tools being updated. Delay is caused by delay to launch of new cluster
Regular Monthly reports | Delivery of monthly reports | 3 reports | 3 reports | 3 reports | 3 reports | 3 report | 7 reports submitted, though need to work on submitting them on time.
Processes for Department | Create and document processes for user management |  | Update and implment process for user Management | Get processes approved by RCC and SVP |  | Get processes approved by RCC and SVP | Updated process for User management and it has been endorsed by RCC. Process is being implemented. Will send details to SVP for approval
| Create and document processes for resource management |  |  | Complete process for 2 services | Get processes approved by RCC and SVP | Complete process for 2 services | Resource allocation process for VM's drafed. Resource allocation process for HPC completed and endorsed by RCC
Training plan for all department staff | All staff should attend at least one training course a year | [5 empty] | Training for 3 staff on new cluster administration completed in May.