## Sheet1
Order | VM | DNS Name | OS | Primary IP Address | Network #1 | NEW VLAN | New IP | DNS Update | LDAP | IP Change | Notes
1 | ku1rpwexv001 | ku1rpwexv001 | Ubuntu Linux (64-bit) | 10.192.26.10 | ANK-RES-PROD | KU-RES-PROD | 10.192.26.10 | NO | Yes | No | VM Migration completed on 8th July 2021
1 | ku1ruwexv001 | ku1ruwexv001 | Ubuntu Linux (64-bit) | 10.192.28.10 | ANK-RES-UAT | KU-RES-PROD | 10.192.26.15 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
1 | KU2RPAAWV005 | KU2RPAAWV005.minet.ae | Microsoft Windows Server 2016 (64-bit) | 10.192.26.12 | ANK-RES-PROD | KU-RES-PROD | 10.192.26.12 | NO |  | No | VM Migration completed on 8th July 2021
1 | KU2RPAAWV006 | KU2RPAAWV006.minet.ae | Microsoft Windows Server 2016 (64-bit) | 10.192.26.13 | ANK-RES-PROD | KU-RES-PROD | 10.192.26.13 | NO |  | No | VM Migration completed on 8th July 2021
1 | KU2RPAAWV007 | KU2RPAAWV007.minet.ae | Microsoft Windows Server 2016 (64-bit) | 10.192.26.14 | ANK-RES-PROD | KU-RES-PROD | 10.192.26.14 | NO |  | No | VM Migration completed on 8th July 2021
1 | ku2rpaaxv001 | ku2rpaaxv001.kunet.ae | Ubuntu Linux (64-bit) | 10.192.26.11 | ANK-RES-PROD | KU-RES-PROD | 10.192.26.11 | NO | Yes | No | VM Migration completed on 8th July 2021
2 | linux-app1 | linux-app1 | Ubuntu Linux (64-bit) | 10.106.21.154 | VLAN 621 | KU-RES-PROD | 10.192.26.21 | Yes |  | Yes | VM Migration completed on 8th July 2021
2 | masdar-fog | MASDAR-FOG.minet.ae | Microsoft Windows Server 2008 R2 (64-bit) | 10.106.21.66 | VLAN 621 | KU-RES-PROD | 10.192.26.24 | Yes |  | Yes | VM Migration completed on 27th July 2021
2 | MI-homeserver | mi-homeserver.minet.ae | Ubuntu Linux (64-bit) | 10.106.21.23 | VLAN 621 | KU-RES-PROD | 10.192.26.35 | Yes | Yes |  | VM Migration completed on 8th July 2021
2 | mila-prod | mila-prod.minet.ae | Red Hat Enterprise Linux 6 (64-bit) | 10.106.21.151 | VLAN 621 | KU-RES-PROD | 10.192.26.36 | Yes |  | Yes | VM Migration completed on 8th July 2021
3 | mi-geodb-prod | mi-geodb-prod | Ubuntu Linux (64-bit) | 10.106.0.211 | VLAN 505 | KU-RES-PROD | 10.192.26.16 |  |  | Yes | VM Migration completed on 8th July 2021
3 | mill-prod | mill.minet.ae | Red Hat Enterprise Linux 6 (64-bit) | 10.106.0.158 | VLAN 505 | KU-RES-PROD | 10.192.26.17 | Yes |  | Yes | VM Migration completed on 8th July 2021
3 | mill-prod2 | mill-prod2.minet.ae | CentOS 4/5/6/7 (64-bit) | 10.106.0.159 | VLAN 505 | KU-RES-PROD | 10.192.26.18 | Yes |  | Yes | VM Migration completed on 8th July 2021
3 | cesam-geodb-prod | cesam-geodb-prod | Ubuntu Linux (64-bit) | 10.106.21.70 | VLAN 621 | KU-RES-PROD | 10.192.26.19 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
3 | cesam-geodb-uat | cesam-geodb-uat | Ubuntu Linux (64-bit) | 10.106.21.64 | VLAN 621 | KU-RES-PROD | 10.192.26.47 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
3 | mi-geodb-dev | mi-geodb-dev | Ubuntu Linux (64-bit) | 10.106.31.3 | VLAN631-DEV | KU-RES-PROD | 10.192.26.34 | Yes |  | Yes | VM Migration completed on 8th July 2021
3 | pdk-server | pdk-server.minet.ae | CentOS 4/5/6/7 (64-bit) | 10.106.21.63 | VLAN 621 | KU-RES-PROD | 10.192.26.37 | Yes |  |  | VM Migration completed on 8th July 2021
4 | masdar-airquality | masdar-airquality | Ubuntu Linux (64-bit) | 10.106.21.73 | VLAN 621 | KU-RES-PROD | 10.192.26.22 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-error | masdar-error | Ubuntu Linux (64-bit) | 10.106.21.74 | VLAN 621 | KU-RES-PROD | 10.192.26.23 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-fog_restored | MASDAR-FOG-2.minet.ae | Microsoft Windows Server 2008 R2 (64-bit) | 10.106.21.79 | VLAN 621 | KU-RES-PROD | 10.192.26.25 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | masdar-marine | masdar-marine | Ubuntu Linux (64-bit) | 10.106.21.72 | VLAN 621 | KU-RES-PROD | 10.192.26.26 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-ocean | masdar-ocean.minet.ae | Ubuntu Linux (64-bit) | 10.106.21.68 | VLAN 621 | KU-RES-PROD | 10.192.26.27 | Yes | Yes | Yes | VM Migration completed on 27th July 2021
4 | masdar-postproc | masdar-postproc | Ubuntu Linux (64-bit) | 10.106.21.75 | VLAN 621 | KU-RES-PROD | 10.192.26.28 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-rems | masdar-rems.minet.ae | Microsoft Windows Server 2012 (64-bit) | 10.106.21.69 | VLAN 621 | KU-RES-PROD | 10.192.26.29 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | masdar-rems2 | masdar-rems2 | Ubuntu Linux (64-bit) | 10.106.21.59 | VLAN 621 | KU-RES-PROD | 10.192.26.30 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-roms | masdar-roms | Ubuntu Linux (64-bit) | 10.106.21.71 | VLAN 621 | KU-RES-PROD | 10.192.26.31 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | masdar-solartechsimulators | masdar-solartechsimulators | Ubuntu Linux (64-bit) | 10.106.21.31 | VLAN 621 | KU-RES-PROD | 10.192.26.32 | Yes - from minet.ae |  | Yes | VM Migration completed on 8th July 2021
4 | masdar-stratobus | masdar-stratobus.minet.ae | Ubuntu Linux (64-bit) | 10.106.21.67 | VLAN 621 | KU-RES-PROD | 10.192.26.33 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
4 | research10 | research10 | CentOS 4/5/6/7 (64-bit) | 10.106.21.25 | VLAN 621 | KU-RES-PROD | 10.192.26.38 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research11 | research11 | CentOS 4/5/6/7 (64-bit) | 10.106.21.26 | VLAN 621 | KU-RES-PROD | 10.192.26.39 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research12 | research12 | CentOS 4/5/6/7 (64-bit) | 10.106.21.27 | VLAN 621 | KU-RES-PROD | 10.192.26.40 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research15 | research15.minet.ae | Microsoft Windows 7 (64-bit) | 10.106.21.38 | VLAN 621 | KU-RES-PROD | 10.192.26.41 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research17 | research17.minet.ae | Microsoft Windows 7 (64-bit) | 10.106.21.40 | VLAN 621 | KU-RES-PROD | 10.192.26.42 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research18 | RESEARCH18.minet.ae | Microsoft Windows 7 (64-bit) | 10.106.21.42 | VLAN 621 | KU-RES-PROD | 10.192.26.43 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research19 | research19.minet.ae | CentOS 4/5/6/7 (64-bit) | 10.106.21.43 | VLAN 621 | KU-RES-PROD | 10.192.26.44 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | research21 | research21.minet.ae | CentOS 4/5/6/7 (64-bit) | 10.106.21.46 | VLAN 621 | KU-RES-PROD | 10.192.26.45 | Yes |  | Yes | VM Migration completed on 8th July 2021
4 | Research22 | research22.minet.ae | CentOS 4/5/6/7 (64-bit) | 10.106.21.47 | VLAN 621 | KU-RES-PROD | 10.192.26.46 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | cesam-web-prod | cesam-web-prod | Ubuntu Linux (64-bit) | 192.168.232.26 | VLAN 17 | KU-RES-DMZ | 10.192.27.10 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | cesam-web-uat | cesam-web-uat | Ubuntu Linux (64-bit) | 192.168.232.52 | VLAN049 | KU-RES-DMZ | 10.192.27.11 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | moccae-web-dev | moccae-web-dev | Ubuntu Linux (64-bit) | 192.168.232.40 | VLAN 34 | KU-RES-DMZ | 10.192.27.12 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | moccae-web-uat | moccae-web-uat | Ubuntu Linux (64-bit) | 192.168.232.51 | VLAN 49 | KU-RES-DMZ | 10.192.27.13 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | recrema-web-prod | recrema-web-prod | Ubuntu Linux (64-bit) | 192.168.232.28 | VLAN 17 | KU-RES-DMZ | 10.192.27.14 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | recrema-web-uat | recrema-web-uat | Ubuntu Linux (64-bit) | 192.168.232.50 | VLAN 49 | KU-RES-DMZ | 10.192.27.15 | Yes | Yes | Yes | VM Migration completed on 8th July 2021
5 | atlas-prod | atlas-prod.masdar.ac.ae | Ubuntu Linux (64-bit) | 10.106.21.50 | VLAN 621 | KU-RES-DMZ | 10.192.27.16 | Yes |  | Yes | VM Migration completed on 8th July 2021
| masdar-pproc | masdar-pproc.minet.ae | Microsoft Windows Server 2008 R2 (64-bit) | 10.106.21.29 | VLAN 621 | [5 empty] | VM Migration not done as issues with data migration