| Meeting name: KUTC Steering Committee (SC) Meeting | Time | 10:00 ~ 11:00 am (UAE time) |
| --- | --- | --- |
| Location: Video Conference (MS Teams Meeting) |  |  |
| Date: Monday, 06 July 2020 |  |  |

| Attendees |  |
| --- | --- |
| KBSI | KU |
| Dr. Hyung-shik Shin, President | Steve Griffith, SVP Research & Development |
| Dr. Hae Jin Kim, Director of KUTC (KBSI) | Prof. Daniel Choi, Director of of KU-Korea Partnerships (KU) |
|  | Dr. Jérémie Pelletier, Manager of KUTC |

Agenda Items

- Status of the action items from the previous SC

- Progresses and achievements for the first-half of 2020 (KBSI, KU)

- Research equipment support plan

- New Joint R&D projects

- Workshop (International Collaborative Workshop) and Next SC

- New KUTC office and lab

- National Materials Science Center (NMSC)

Minutes

- Status of the action items from the previous SC : - Set date of next meeting (Completed); Dr Jérémie Pelletier. - Develop framework, planning any KPI for collaborative projects. Two distinct models to be explored : (1) KBSI staff to help improve protocols capability and (2) KBSI staff to contribute to new projects from external funding and potentially internal funding. - Status: KBSI Staffs to help improve protocols capability and contribute new project from external and internal funding; The Protocol capability has fruitful result to relate microscope research sectors through Dr. Baik; The new KUTC office space and visa for long-term stay should be considered; In advance, the status of the joint research agreement is to promote a simplified plan regarding access.; Dr Jérémie Pelletier. - Development of KU internal funding program to be aligned to have a few projects specifically with KBSI as partner based on ‘Co-funding mechanism’. - Status: KU’s Budget for new joint projects will be available from next year; Outline of the procedures for the directed call for the proposals has been developed as a result of discussion between two directors (Dr. Kim and Dr. Daniel); Prof. Daniel Choi & Blake Ashwell. - Update on relocation progress and development on CORE lab implementation (including timeline and sequencing) - Status: It’s still in proress.; Dr Jérémie Pelletier.

- Progresses and achievements for first-half of 2020 (KBSI, KU) : - Research equipment support : - Dr. Baik supported TEM for 3 month in the area of research, analysis, operation and training lecture. His contribution is extended to consult research. (Achievement : 2 journal papers in preparation, 1 joint research in discussion ) - New demands for KBSI experts : Demands for FIB, XRD, XPS and some instruments to be installed in KU sooner or later, such as NMR and Mass spectrometer, are discussed. - On-going joint R&D project: - The joint R&D project(Devolopment of solid electrolytes for harsh environment battery application, KBSI (Dr. Kim Hae-Jin), KU (Prof. Choi)) between KBSI-KU approved in the previous SC is going smoothly. - New potential 2 projects proposed by KU (still in discussion). - Reducing CO2 gas by Absorption, Catalysis (KU/Prof. Kyriyaki). - Sulfur, Sulphate for Li-S batteries (Cathode) and Silica nano particle for catalysis, adsorption (KU/Prof. Saeed). - Development of virus diagnosis technique (KU/Prof. Habiba)

- Research equipment support plan : - KBSI agreed to dispatch experts for FIB, XRD, XPS to KU later than the coming September in case the threat of COVID19 has decreased to an appropriate level. - KBSI is available to dispatch experts for NMR and Mass Spectrometer. The timing and the way will be discussed later in relation to the KU’s installation plan. - A new type of demands for the research expert for joint research discussion and analysis in the BTC will be reviewed and discussed separately. - A on-line meeting for the KUTC management (Dr. Kim, Prof. Choi and Dr. Jeremie) to discuss issues and plans and to monitor the action items for this meeting will be held regularly.

- Development of new Joint R&D projects: - The funding model for the new proposed projects will be decided after the discussion inside KU. (If KU researchers need additional funding for the projects, they are recommended to follow the KU internal funding mechanism, such as the proposal calls in KU) - New 2021 joint R&D topics are to be decided. Prof. Choi will organize internal KU workshops to solicit ideas and present results to the KUTC SMB at the next meeting. - Developing collaboration projects under KUTC is conducted by directed call for proposals in KU. 1. Identify KBSI focused area leads & prepare focused area descriptions 2. Announce call for white papers 3. Submission of white papers by KU faculty identifying KBSI focused area lead 4. Invite to write full proposals by selection committee (KUTC directors, KU center directors, KBSI focused area leads) 5. Submission of full proposals Jointly 6. Recommendation of the projects by proposal’s selection committee 6. Approval of the recommended projects by the KUTC SMB 7. Kick off the awarded projects - A on-line meeting for the KUTC managers (Dr. Kim and Prof. Choi) to discuss new joint R&D projects will be held regularly.

- Workshop (ICW) and Next SC : - The workshop and 3rd steering committee meeting will be held in November or early December 2020 virtually. - The workshop schedule will be settled in consideration of the kick-off of the new joint R&D projects.

- Relocation of KUTC office and lab : - Discussions and agreement on the relocation of KUTC office and lab space should be finalized prior to the dispatch of KBSI experts. - The problem of KUTC space will be guided to KBSI considering Prof. Choi’s strategic view and Dr. Jeremie’s facility space utilization as much as possible.

- National Materials Science Center (NMSC) - KBSI, as a key partner of KU, agreed to KU’s plan to establish NMSC and will actively throughout the entire process from the planning to the operation. - A on-line meeting for key persons(Dr. Kim and Prof. Choi) will be held regularly. KU will form a working group to proceed it.

Action Items

Research equipment support plan : - FIB, XRD, XPS equipment experts of KBSI will be dispatched to KU, possibly in September, but the specific timing will be decided after considering the progress of the COVID 19 pandemic. (Dr. Kim, Prof. Choi, Dr. Jeremie) - KU will share with KBSI its plan on installation of NMR and MS. (Dr. Jeremie)

Relocation of KUTC office and lab : - Working space for KUTC experts should be secured prior to the dispatch. (Dr. Jeremie) Discussions on relocation of KUTC office and the KUTC lab will be followed by the regular on-line meeting for the KUTC managers. (Dr. Kim, Prof. Choi, Dr. Jeremie)

Worshop(ICW) : - Dr. Kim and Prof. Choi will find a date of workshop and the 3rd steering committee meeting between November to early December 2020. (Dr. Kim and Prof. Choi)

National Materials Science Center (NMSC) - KU will develop strategic plans to collaborate with key local & international organizations. (Prof. Choi)

Development of new joint projects - KU and KBSI will jointly develop a directed call for proposals in KU . (Prof. Choi) - KBSI will identify the the areas of interest (Dr. Kim)