| Meeting name: KUTC Steering Committee (SC) Meeting | Time | 10:00 ~ 11:00 am (UAE time) |
| --- | --- | --- |
| Location: Video Conference (MS Teams) |  |  |
| Date: Thursday, 10 December 2020 |  |  |

| Attendees |  |
| --- | --- |
| KBSI | KU |
| Dr. Hae Jin Kim, Director of KUTC (KBSI) | Steve Griffith, SVP Research & Development |
|  | Prof. Daniel Choi, Director of KUTC |
|  | Dr. Jérémie Pelletier, Lab acting director (Manager of KUTC) |

Agenda Items

- Status of the action items from the previous S.C.

- Research equipment support plan

- Development of new Joint R&D projects

- Relocation of KUTC office and lab

Minutes

- Status of the action items from the previous SC : Research equipment support - The possible dispatching timing of FIB, XRD, XPS equipment experts of KBSI will be decided after considering the progress of the COVID 19 in the first half of 2021.; Dr. Kim Hae Jin Prof. Choi Dr. Jeremie. Development of new joint R&D - KBSI internal funding program was aligned to have all projects with KU as a partner based on ‘Co-funding mechanism’ and will follow the KU’s 2021 funding plan. - KU and KBSI will jointly develop new Korea-UAE joint R&D after the Joint R&D workshop in first-half 2021.; Dr. Kim Hae Jin Prof. Choi. Relocation of KUTC office and lab : - After arrangement of moving period of KU, KUTC office will be relocated in SAN campus, KU. - KBSI will start to setting up the KUTC lab by following KU’s situation in first-half 2021.; Dr. Kim Hae Jin Prof. Choi Dr. Jeremie. Korea-UAE Joint R&D Workshop: - KBSI and KU are preparing workshop between January and February in 2021.; Dr. Kim Hae Jin Prof. Choi. National Materials Science Center (NMSC) - KU will develop strategic plans to collaborate with key local & international organizations with KBSI.; Dr. Kim Hae Jin Prof. Choi.

- Research equipment support plan - KBSI-KU agreed to dispatch experts for FIB, XRD, XPS to KU on first-half of 2021. - KBSI shared information of ‘Fast track’ process by considering the progress of the COVID19 in UAE for dispatching KBSI experts to KU as a result of agreement between Korea and UAE government.

- Development of new Joint R&D projects - KBSI identified the new candidate topics (Korea side) for the new Korea-UAE joint R&D (Total 6 topics) 1. Atomic scale analysis using aberration corrected TEM (Dr. Hionsuck Baik, KBSI) 2. Correlative light and electron microscopy (CLEM) for imaging the cellular function and ultrastructure (Dr. Kyung-bok Lee, KBSI) 3. Development of cathode components for high sulfur loading Li-S battery (Dr. Hee Jin Kim, KBSI) 4. Development of selective CO2 capture based on organic/inorganic nanomaterials with hollow structure (Dr. Jin Bae Lee, KBSI) 5. Electrosynthesis of hydrocarbons with more carbon atoms (> C2) (Dr. Beomgyun Jeong, KBSI) 6. Surface and interface studies with XPS (Dr. Hyung Joong Yun, KBSI) - KU expressed concerned about additional joint project (Hee Jin Kim’s proposed topic) in the area of batteries. - KU and KBSI agreed to organize Joint R&D workshop on January 2021 by inviting KBSI researchers (who proposed the topics) and KU faculties who might be interested in joint projects with KBSI. - Developing collaboration projects under KUTC is conducted by directed call for proposals in KU. 1. Identify KBSI focused area leads & prepare focused area descriptions (2020.12) 2. Workshop with KBSI focused area leads and potential KU counterpart (KU RICH/CeCaS/Non-center Faculty) (2021.01) 3. Announcing call for white papers (2021.02) 4. Submission of white papers by KU faculty identifying KBSI focused area lead (2021.03) 5. Invite to write full proposals by selection committee (2021.04) (By KUTC directors, KU center directors, KBSI focused area leads) 6. Submission of full proposals Jointly (2021.05) 7. Selection of the projects by proposal selection committee (2021.06) (By KUTC directors, KU & KBSI management) 8. Kick off the awarded projects (2021.07)

- Relocation of KUTC office and lab - KUTC office is relocated in room 8377, Arzanah, SAN campus, KU - KBSI expressed importance of the independent KUTC office. As a support project of the Korean government, independent space is needed to properly respond for promotion to KUTC visits. - KU (Jeremie) briefed progress in development of KUTC office space with KU space plan of 2021 year. - KU (Jeremie) brifed progress in development of KUTC lab space. It’s being taken care of by KU Space Planning team. – - After Core-lab movement will be finished until Q2 2021 in KU, KUTC lab set up will be started on Q3 2021. Before setting up the KUTC lab, research work of dispatching KBSI researcher will be performed in prof. Choi’s new Lab at SAN Campus (SAN campus, building 3, Lab 3019, ground floor). - Equipments for KUTC lab to be purchased and set up by KBSI except fume hood and water / electrical supply.

Action Items

Research equipment support plan - KBSI-KU agreed to dispatch experts for FIB, XRD, XPS from KBSI to KU on first-half of 2021. By sharing the situation of CORE labs in KU, possible dispatching timing, period and the exact demands of equipment experts dispatch for each CORE labs will be discussed until Q1 2021.

Relocation of KUTC office and lab - KU and KBSI will sharing the status of KU moving progress related to CORE labs and help for research equipment support and KUTC joint R&D in company with each other. - KU (Jeremie) briefed progress in development of KUTC office and lab space by considering KU’s space reloation status and will share space relocation planning of 2021 year with KBSI. - After Arzanah retrofitting & CORE-lab movement will be finished until Q2 2021 in KU, the installation of KUTC lab will be started on Q3 2021y. - The installation of KUTC lab will be started after CORE-lab movement in KU (about Q3 2021y).

Developing collaboration New R&D projects & Joint R&D Worshop - KU and KBSI will jointly develop new Korea-UAE joint R&D related to Joint R&D workshop on January 2021 and will follow the KU’s 2021 R&D funding plan. - The Korea-UAE Joint R&D workshop for developing new R&D projects by KBSI focused area leads and potential KU counterpart will be organized on January 2021.