## Slide 1: Information for Oct. 28th KUTC Steering Committee Meeting
October 21, 2021
Khalifa University of Science and Technology
1
Daniel Choi

## Slide 2: KUTC Office
2
Location: Room 8377 at Arzanah
Furniture: 6 desks and 6 chairs
Electricity is available.

## Slide 3: KUTC Lab
3
Location: Room 8022 at Arzanah
Electricity is not available - Electrical wiring work is pending until ADDC’s
approval

## Slide 4: KUTC Lab (Cont’d)
4
Two crates are ready for shipping to KU from KBSI as of 20th of Oct.(total 2 Crates):
The crates contain KBSI’s lab consumables and small lab tools (scale, etc.) for KBSI’s lab work @ KUTC
Photo of ‘inside of the crate’
Photo of ‘crate after closing’

## Slide 5: Status of KUTC project and highlights in activities
5
KUTC Project: “Development of solid electrolytes for harsh environment”
- Project period: Nov. 2019 – Oct 2022 (in progress)
2nd KUTC Joint Workshop 2021 (Virtual): Advanced Materials
- Date: 3rd February 2021
- Participants: 10 KU faculty members and 6 KBSI researchers
The project on hydrogen (sponsored by UAE government and Korean government):
“Technology development for hydrogen based transport infrastructure in UAE”
- Four year project: 2021 - 2025
- KUTC’s engagement was requested by Korea Transport Institute (KOTI under Korea Ministry of
Land, Infrastructure and Transport)
https://english.koti.re.kr/
- KOTI delegation’s visit to UAE in November 2021 for discussion on working group work.

## Slide 6: Proposed change in status of KUTC
6
Changing KUTC ‘Center’ to a ‘Joint Lab’ at some point. (Discussion on developing new collaboration projects may need to be reserved)
Program for faculty, student and researcher exchanges can be sustained.
At some point in the future, once the UAE R&D agenda is moving ahead, we can look for opportunities to build this back up (Until then Steering Committee may not be needed).