| # Khalifa University Enterprises Company Operational Committee Meeting | ### 01- Sep- 2022 ### 3-4 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Mr. Ahmed Al Neyadi (Chairman) Dr. Arif Al Hammadi (Member) Mr. Ebrahim Jafar Alahmed (Member) Dr. Sami Bashir (Invitee) Mr. Hesham Salem (Invitee) Mr. Osama Al Najjar (Invitee) ## Absent: No absents Dr. Steve Griffiths (SVP- Research and Development -Invitee) |  |  |  |

# Agenda Items

## The meeting agenda Items:-

- Ankabut company next step (Mr. Ebrahim /Mr. Hesham -  5 Minutes).

- KUEC Delegation of Authority – (Mr. Ebrahim - 5 Minutes) .

- Legal agreement between KU & KUEC (Mr. Osama - 5 minutes).

- Laboratories commercialization project (Mr. Hesham - 5 minutes).

- Baynouna project and partnership with Unilab . (Mr. Hesham -  5 Minutes).

- KUEC financial statements 2021 - (Mr. Ebrahim - 5 Minutes) .

- Administrative workforce support in KUEC.

# Action Points

1- Ankabut company next step (Mr. Ebrahim /Mr. Hesham -  5 Minutes).

.

a- The investment committee approval stage finished.

b- The establishing of the new Ankabut company in the final stage.

Timeline: 15 Sep 2022

2- KUEC Delegation of Authority – (Mr. Ebrahim - 5 Minutes) .

- Mr. Ahmed asked to make it more determined by removing ranges and keeping fixed percentages for each sharing level.

- Dr. Sami said he would work on it and provide the new faculty sharing model.

Timeline: 15 Sep 2022

3- Legal agreement between KU & KUEC.

- Mr. Ahmed asked Mr. Osama to expedite the legal agreement approval, which will solve many issues faced by KUEC in its relation with KU, such as revenue sharding.

Timeline: 15 Sep 2022

4- Commercialization of KU Laboratories. .

- Mr. Ahmed asked to expedite the project as it took more than expected, Hesham informed the committee that the project under progress and he will do his best to expedite the process.

Timeline: 30 Sep 2022

5- The Baynouna project to resume production and partnership with Unilab .

- Dr. Arif asked to partner with Unilab directly and avoid any conflict of interest that could happen through small individual companies.

- Hesham contacted Unilab to start a new round of negotiations for a new partnership proposal., still no response received.

Timeline: 30 Sep 2022

6- KUEC financial statements 2021.

Mr. Ebrahim updated the committee that the auditors had already assigned, and we received the first FS draft under review.

Timeline: 25 Sep 2022

7- Administrative workforce support in KUEC.

- Mr. Ebrahim raised the point of the need for administrative assistance in KUEC to do the workload instead of using the KU team.

- Mr. Ahmed approved the concept but postponed it until the approved delegation of authority was ready and approved by the IC.

Timeline: 15 Oct 2022