| # Khalifa University Enterprises Company Operational Committee Meeting | ### 03 - Nov- 2022 ### 3-4 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Dr. Arif Al Hammadi (Member) Mr. Jalal Al Jazzar (Invitee) Mr. Ebrahim Jafar Alahmed (Member) Dr. Sami Bashir (Invitee) Mr. Hesham Salem (Invitee) Mr. Osama Al Najjar (Invitee) ## Absent: No absents Mr. Ahmed Al Neyadi (Chairman) Dr. Steve Griffiths (SVP- Research and Development -Invitee) |  |  |  |

# Agenda Items

## The meeting agenda Items:-

- Ankabut company's next step (Mr. Ebrahim /Mr. Hesham - 5 Minutes).

- Ceramic – Dr. Sami ( 5 Minutes).

- Swift Biomed – Dr. Sami ( 5 Minutes).

- Administrative manpower support in KUEC (Mr. Ebrahim - 5 Minutes).

- A legal agreement between KU & KUEC (Mr. Osama - 5 minutes).

- Laboratories commercialization project (Mr. Hesham - 5 minutes).

- Baynouna project to resume production and partnership with Unilab (Hesham- 5 Minutes).

- NAVA Mask registration process. (Mr. Hesham - 5 minutes).

- Bicycle project.

# Action Points

1- Ankabut company next step (Mr. Ebrahim /Mr. Hesham - 5 Minutes).

a- will arrange a meeting with Mr. Fahem and Finance team (Mr. Jalal / Mr. Ebrahim) to discuss the transition period and next steps.

b- The main milestone in the transition period ( New Financial System- Ankabut internal Policies- Vacancies- accounting positions).

c- Ankabut needs a governing board.

Timeline: 31 Dec 2022

2- Ceramic – Dr. Sami ( 5 Minutes) .

- Mr. Sami will try to reach out to the involved team to get their pitch decks and share them with members.

Timeline: 30 Nov 2022

3- Swift Biomed – Dr. Sami ( 5 Minutes) .

- Mr. Sami will try to reach out to the involved team to get their pitch decks and share them with members.

Timeline: 30 Nov 2022

4- Administrative manpower support in KUEC (Mr. Ebrahim - 5 Minutes) .

- The committee assured the importance of administrative assistance to operate the proposed projects and justify revenue sharing with KU.

Timeline: 30 Dec 2022

5- Legal agreement between KU & KUEC.

- Arranging a meeting with Mr. Osama and Finance team (Mr. Jalal / Mr. Ebrahim) to discuss the suitability of the current proposed agreement between KU and KUEC and the new IP contract.

Timeline: 27 Oct 2022

6- Commercialization of KU Laboratories. .

- Hesham briefed the committee about the progress of the website

- Many requests received from clients in UAE are in progress.

Timeline: 27 Oct 2022

7- The Baynouna project to resume production and partnership with Unilab .

- Mr. Jalal asked for more time to review the feasibility of establishing companies for each project and advised using the SPV concept for new projects.

Timeline: 31 Dec 2022

8- NAVA Mask registration process.(Mr. Hesham - 5 minutes).

- Hesham explained the need to sign the registration agreement for the NAVA mask to be certified according to European standards (CE Marking).

Timeline: 30 Nov 2022

9- Bicycle project.

- Dr. Arif explained the importance of establishing the Bicycle Company to finalize the registration of the new bicycle brand.

Timeline: 30 Nov 2022