| # Khalifa University Enterprises Company Operational Committee Meeting | ### 13 - Oct- 2022 ### 3-4 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Mr. Ahmed Al Neyadi (Chairman) Dr. Arif Al Hammadi (Member) Mr. Jalal Al Jazzar (Invitee) Mr. Ebrahim Jafar Alahmed (Member) Mr. Hesham Salem (Invitee) Mr. Osama Al Najjar (Invitee) ## Absent: No absents Dr. Steve Griffiths (SVP- Research and Development -Invitee) Dr. Sami Bashir (Invitee) |  |  |  |

# Agenda Items

## The meeting agenda Items:-

- Ankabut company next step (Mr. Ebrahim /Mr. Hesham -  5 Minutes).

- KUEC Delegation of Authority – (Mr. Ebrahim - 5 Minutes) .

- Legal agreement between KU & KUEC (Mr. Osama - 5 minutes).

- Laboratories commercialization project (Mr. Hesham - 5 minutes).

- Baynouna project and partnership with Unilab . (Mr. Hesham -  5 Minutes).

- KUEC financial statements 2021 - (Mr. Ebrahim - 5 Minutes) .

- Administrative workforce support in KUEC.

# Action Points

1- Ankabut company next step (Mr. Ebrahim /Mr. Hesham -  5 Minutes).

.

- Arranging a meeting with Mr. Fahem and Finance team (Mr. Jalal / Mr. Ebrahim) to discuss the treansision period and next step.

- Main milestone in the transition period ( New Financial System- Ankabut internal Policies- Vacancies- accounting positions).

- Ankabut need a governing board.

- Mr. Ebrahim to send the curve-out study to Mr. Jalal.

- Start Anabut operation January 2023 as a target.

Timeline: 31 Dec 2022

2- KUEC Delegation of Authority – (Mr. Ebrahim - 5 Minutes) .

- Mr. Ahmed asked to postpone thois point and remove from the agenda as it is still early in this stage.

Timeline:

3- Legal agreement between KU & KUEC.

- Arranging a meeting with Mr. Osama and Finance team (Mr. Jalal / Mr. Ebrahim) to discuss the suitability of the current proposed agreement between KU and KUEC and the new IP contract.

- Mr. Ahmed and Dr. Arif think the current proposed format is enough to the current stage.

Timeline: 27 Oct  2022

4- Commercialization of KU Laboratories. .

- Hesham briefed the committee about the progress in the website

- Many request received from clients in UAE under progress.

- Dr. Arif asked to send the website link to Comunication department for their review and confirmation regarding the design and suitability to KU website.

Timeline: 27 Oct 2022

5- The Baynouna project to resume production and partnership with Unilab .

- Hesham contacted Unilab to start a new round of negotiations for a new partnership proposal., still no response received.

- Mr. Jalal asked to give more time to review the feasibility of establishing companies for each project and advised to use the concept of SPV for new projects.

Timeline: 31 Dec 2022

6- KUEC financial statements 2021.

Mr. Ebrahim updated the committee that final FS issued and sent to ADGM for licensing purpose within the

Timeline: 25 Sep 2022

7- Administrative workforce support in KUEC.

- Mr. Ahmed to postpone this point and remove from the agenda.

Timeline