| # Khalifa University Enterprises Company Operational Committee Meeting | ### 11 Feb 2022 ### 2-3 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Dr. Arif Al Hammadi (Member) Mr. Ebrahim Jafar Alahmed (Member) Dr. Sami Bashir (Invitee) Mr. Hesham Salem (Invitee) ## Absent: Mr. Ahmed Al Neyadi (Chairman) Dr. Steve Griffiths (SVP- Research and Development-Member) Mr. Osama Al Najar (Invitee) | ) (Invitee) |  |  |

# Agenda Items

| ## The meeting agenda Items :- |  |  |  |
| --- | --- | --- | --- |

- Ankabut new company project updates (5 minutes)- Mr. Ebrahim

- Royalty/Equity model for faculties contributing IP/efforts in the new companies (10 Minutes) Dr. Sami

- TechStars project updates (5 Minutes) Dr. Sami .

- Nava Mask JV updates (5 minutes)- Mr. Hesham Salem.

- KUEC Delegation of Authority (10 minutes)- Mr. Ebrahim

- KUEC new subsidiaries establishments. (5 minutes) Mr. Hesham .

- JP Morgan tax declaration updates ( 5 minutes)- Mr. Ebrahim.

- JP Morgan reporting (5 minutes) Mr. Hesham .

- Commercialization of KU Laboratories. (5 minutes)- Mr. Hesham.

- Any other points (5 minutes).

# Action Points

  - Ankabut project updates:- ensure that PWC commits to the study completion deadline (Mr. Ebrahim).

a-    Provide PWC with the required data (Mr. Hesham & Fahem).

b-   Mr. Ebrahim sent an email to PWC to remind them that the study deadline is already due.

    - Timeline: Week of 31st January

  - Royalty/Equity model for faculties contributing IP/efforts in the new companies (10 Minutes) Dr. Sami .

      - Dr. Sami presented a summary model for the relation between KU and KUEC regarding KU Lab's IP investments and usage.

      - Dr. Arif asked for a detailed study of the faculty compensation/ equity in the new projects, representing the study's core importance.

    - Timeline: Week of 22nd February

  - TechStars project updates (5 Minutes) Dr. Sami .

      - Dr. Sami will provide a report about the Techstars project progress.

- Timeline: Week of 22nd February

  - Nava Mask JV updates (10 minutes)- Mr. Hesham

      - Dr. Sahdi arranged two meetings with both potential investors ( B&A- German Company); the discussion is in progress, awaiting the final approval to start the proposed 2 JVs.

      - Hesham sent two emails to DoH for collaboration regarding the new mask; no responses were received from them.

      - Signing the NDA will need more time to finalize the licensing of IP from KU to be legally valid will postpone till we have the proper legal support.

- Timeline: Week of 22nd February

  - KUEC Delegation of Authority (10 minutes)- Mr. Ebrahim - Mr. Hesham.

      - Mr. Ebrahim provided a quick review of the new proposed authority matrix, awaiting Mr. Ahmed to provide his opinion and confirmation.

          - Timeline: Week of 22nd February

  - KUEC new subsidiaries establishments. (10 minutes) Mr. Hesham.

      - To establish governing part of the new authority matrix to handle the legal relationship between KU and KUEC (Dr. Sami - Mr. Hesham – Mr. Osama).

    - Timeline: Week of 22nd February

  - JP Morgan tax declaration updates ( 5 minutes)- Mr. Ebrahim.

      - Mr. Ebrahim confirmed that all required tax declaration forms were provided to JP Morgan as per their request.

    - Timeline: Done

  - JP Morgan reporting (5 minutes) Mr. Hesham.

      - Hesham sent all the reporting inquiries to Mr. Ahmed regarding the Black Rock investments to review and advise the answers

    - Timeline: Week of 22nd February

  - Commercialization of KU Laboratories. (5 minutes)- Mr. Hesham.

      - Hesham Updated the committee that a new director was assigned to the laboratories of KU; we met the new director (Dr. Peter) and discussed our commercialization project; he is ok to support us in the remaining steps of the commercialization project.

- Timeline: Week of 31st  March

  - Any other points (5 minutes)