| # Khalifa University Enterprises Company Operational Committee Meeting | ### 11- Aug- 2022 ### 3-4 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Mr. Ahmed Al Neyadi (Chairman) Dr. Arif Al Hammadi (Member) Mr. Ebrahim Jafar Alahmed (Member) Dr. Sami Bashir (Invitee) Mr. Hesham Salem (Invitee) ## Absent: No absents Dr. Steve Griffiths (SVP- Research and Development -Invitee) Mr. Osama Al Najjar (Invitee) |  |  |  |

# Agenda Items

## The meeting agenda Items:-

- Ankabut projection study (Mr. Ebrahim - 5 Minutes).[ Attached is the projection study]

- Royalty/Equity model for faculties contributing IP/efforts in the new companies (10 Minutes - Dr. Sami).[ Attached is the proposed Model].

- A legal agreement between KU & KUEC

- Laboratories commercialization project (Mr. Hesham - 5 minutes).

- Baynouna project to resume production and partnership with Unilab (Hesham- 5 Minutes) [ Attached is the investment proposal letter].

- Administrative and human resources support in KUEC (Mr. Ebrahim - 5 Minutes).

- Hybrid Memory Project Dr. Sami ( 5 Minutes). [ Attached is the proposed Model]

- Nava Mask JV updates – Dr. Sami ( 5 Minutes).

- KUEC Delegation of Authority - (Mr. Ebrahim - Mr. Ahmed -5 Minutes). [ Attached is the proposed Authority matrix]. (linked with resources point).

- KUEC financial statements 2021 - (Mr. Ebrahim - 5 Minutes).

# Action Points

1- Ankabut projection study (Mr. Ebrahim - 5 Minutes).

a- Mr.Ebrahim submitted to the committee the updated study that contains the sales revenues and costs breakdown, the study confirmed by Mr. Fahem.

b- Mr. Ahmed will review the study and provide his feedback. Then, Mr. Ebrahim can send the study to the investment committee members to approve and establish Ankabut company.

Timeline: 25 Aug 2022

2- Royalty/Equity model for faculties contributing IP/efforts in the new companies (10 Minutes) Dr. Sami.

- Mr. Ahmed asked to make it more determined by removing ranges and keeping fixed percentages for each sharing level.

- Dr. Sami said he would work on it and provide the new faculty sharing model.

Timeline: 25 Aug 2022

3- Legal agreement between KU & KUEC (Mr. Osama - 5 minutes).

- Mr. Ahmed asked Mr. Osama to expedite the legal agreement approval, which will solve many issues faced by KUEC in its relation with KU, such as revenue sharding.

Timeline: 1 Sep 2022

4- Commercialization of KU Laboratories. ( Mr. Hesham- Dr. Steve)

- Hesham update the committee with the follow-up points of the projects as follow:-

- The Website Contents are under review by Dr. Peter.

- IT confirmed that the website is ready to launch.

- We are waiting for Dr. Peter to return from his annual leave to resume the project.

- Providing laboratory services under progress to many clients.

- Mr. Ahmed asked to start the laboratory services under KUEC and not to wait to establish a new company specifically for these activities; this will expedite the project and generate revenues.

Timeline: 1 Sep 2022

5- The Baynouna project to resume production and partnership with Unilab (Hesham Salem 5 Minutes).

- Dr. Arif asked to partner with Unilab directly and avoid any conflict of interest that could happen through small individual companies.

- Hesham will contact Unilab to start a new round of negotiations for a new partnership proposal.

Timeline: 30 Aug 2022

6- Administrative workforce support in KUEC (Mr. Ebrahim - 5 Minutes).

- Mr. Ebrahim raised the point of the need for administrative assistance in KUEC to do the workload instead of using the KU team.

- Mr. Ahmed approved the concept but postponed it until the approved delegation of authority was ready and approved by the IC.

Timeline: 1 Sep 2022

7- Nava Mask JV updates - Mr. Hesham

- Dr. Sami updated the committee with NAVA Mask progress with LAVIE company, KU signed a IP agreement with the company against 50 K, any commercial agreement in the future will be done through KUEC using a business setup model.

Timeline: 1 Oct 2022

8- KUEC Delegation of Authority - Mr. Ebrahim - Mr. Hesham.

Mr. Ahmed will provide the committee the feedback regarding this particular.

Timeline: 01 Sep 2022

9- KUEC financial statements 2021 - Mr. Ebrahim.

Mr. Ebrahim updated the committee that the auditors had already assigned, and we received the first FS draft under review.

Timeline: 15 Sep 2022