| # Khalifa University Enterprises Company Operational Committee Meeting | ### 17- Mar- 2022 ### 2-3 P.M ### Virtual meeting |
| --- | --- |

| ## Meeting called by: KUEC Operational Committee |  | ## Type of meeting: | Semi-weekly |
| --- | --- | --- | --- |
| ## Attendees: |  |  |  |
| Members: Mr. Ahmed Al Neyadi (Chairman) Dr. Arif Al Hammadi (Member) Mr. Ebrahim Jafar Alahmed (Member) Mr. Osama Al Najjar (Invitee) Dr. Sami Bashir (Invitee) Mr. Hesham Salem (Invitee) ## Absent: Dr. Steve Griffiths (SVP- Research and Development -Invitee) |  |  |  |

# Agenda Items

| ## The meeting agenda Items:- |  |  |  |
| --- | --- | --- | --- |

- Ankabut carve-out updates (10 minutes)- Mr. Ebrahim.

- Royalty /Equity model for faculties contributing IP/efforts in the new companies (10 Minutes) Dr. Sami

- TechStars project updates (5 Minutes) Dr. Sami.

- Nava Mask JV updates (5 minutes)- Mr. Hesham Salem.

- KUEC Delegation of Authority (5 minutes)- Mr. Ebrahim.

- KUEC new subsidiaries establishments. (10 minutes) Mr. Hesham.

- KUEC financial statements 2021 (5 minutes)- Mr. Ebrahim.

- KUEC license renewal (5 minutes) - Mr. Osama Al Najjar

- JP Morgan -Black Rock Reporting (5 minutes) Mr. Hesham.

- Commercialization of KU Laboratories. (5 minutes)- Mr. Hesham.

- Any other points (5 minutes).

# Action Points

At the beginning of the meeting, Dr. Arif asked to start the discussion with the previous meeting action point and make sure to meet the determined deadlines.

- Ankabut carve-out updates (10 minutes)- Mr. Ebrahim.

  - Mr. Ebrahim briefly reported about the PWC carve-out report

a-. Mr. Ahmed asked to have another separate meeting to discuss in detail PWC consultants' present.

Timeline: Week of 31st March

  - Royalty/Equity model for faculties contributing IP/efforts in the new companies (10 Minutes) Dr. Sami.

      - Dr. Sami has already prepared a model for the relation between KU and KUEC regarding KU Lab's IP investments and usage and a detailed study of the faculty compensation/ equity in the new projects.

      - Dr. Sami will present the study at the next meeting.

    - Timeline: Week of 31 st Mar

  - TechStars project updates (5 Minutes) Dr. Sami.

      - Dr. Sami will provide a report about the Techstars project progress.

      - Mr. Ahmed will meet Dr. Sami in another separate meeting to coordinate the project results.

- Timeline: Week of 31st- Mar

  - Nava Mask JV updates (10 minutes)- Mr. Hesham

      - It will be discussed in the coming meeting

- Timeline: Week of 31st March

  - KUEC Delegation of Authority (10 minutes)- Mr. Ebrahim - Mr. Hesham.

      - Mr. Ebrahim provided a quick review of the new proposed authority matrix, awaiting Mr. Ahmed to provide his opinion and confirmation.

      - Mr. Ahmed asked to send him the latest updated DOA to be discussed in the coming meeting.

          - Timeline: Week of 31st  Mar.

  - KUEC new subsidiaries establishments. (10 minutes) Mr. Hesham.

      - Dr. Arif and Mr. Ahmed agreed to start establishing new subsidiaries as legal entities without funding to resolve many operational and motivational issues with the new startup's projects; Mr. Osama confirmed that this is part of the operational committee authority as long no major financial transactions involved. (Dr. Sami - Mr. Hesham – Mr. Osama).

      - Hesham will send the first round of new companies' establishment projects.

    - Timeline: Week of 15th April

  - KUEC financial statements 2021 (5 minutes)- Mr. Ebrahim.

      - Mr. Ebrahim presented the status of the FS requirements for KUEC and the proposed audit fees to the committee and will follow up with the ARCC for the final approval.

- Timeline: Week of 30th  April

  - KUEC license renewal (5 minutes) - Mr. Osama Al Najjar

      - Mr. Osama will coordinate with Mr. Hisham regarding the requirements of license renewal and will take the necessary action.

          - Timeline: Week of 15th April

  - JP Morgan reporting (5 minutes) Mr. Hesham.

      - Hesham sent all the reporting inquiries to Mr. Ahmed regarding the Black Rock investments to review and advise the answers.

- Timeline: Week of 31st  March

  - Commercialization of KU Laboratories. (5 minutes)- Mr. Hesham.

      - Hesham Updated the committee that a new director was assigned to the laboratories of KU; we met the new director (Dr. Peter) and discussed our commercialization project; he is ok to support us in the remaining steps of the commercialization project.

- Timeline: Week of 31st  March

  - Any other points (5 minutes)

        - Dr. Arif asked to make sure that the KUEC operation committee early plane the Investment Committee meeting to acquire important decisions efficiently.