## Test
|  |  | Prepared By: | Reviewed By: | Ref: | Documents Reviewed | 1. EHS Annual Inspection Plan (EHS Activities) 2. inspection records samples 3. Internal Audit report 4. Internal Audit action tracker
Client: | Khalifa University | Initials | AE | RB | Test 12
Process: | EHS Review | Date | 2023-06-18 | 2023-06-19
Period: | May 2023- June 2023
Sr | Particulars | Period |  |  |  | Attributes |  |  | Remarks
[6 empty] | A | B | C
1 | EHS Annual Inspection Plan |  |  |  |  | a |  |  | EHS Annual Inspection Plan is obtained
2 | EHS Annual Inspection Records | [5 empty] | X |  | 3 out of 10 smaple inspections were not conducted as per the inspection plan. for 6 inspection reports, delays were noted in sharing the inspection report with stakeholders
3 | Follow-up Mechanism | [6 empty] | X | There was absence of action plan, target date and status in the Internal Audit tracker for the corrective actions identified in the Internal Audit report "FDEHS/REP09-21/OCT/2022". Further, inadequate follow up mechanism (post inspection) to track the open/closed corrective actions covering all the inspection reports
Sampling Technique
Total Population |  | 64
Samples Selected |  | 10
Percentage |  | 15.62%
Tickmarks
A | EHS Annual Inspection Plan is obtained
B | 3 out of 10 smaple inspections were not conducted as per the inspection plan. for 6 inspection reports, delays were noted in sharing the inspection report with stakeholders
C | There was absence of action plan, target date and status in the Internal Audit tracker for the corrective actions identified in the Internal Audit report "FDEHS/REP09-21/OCT/2022". Further, inadequate follow up mechanism (post inspection) to track the open/closed corrective actions covering all the inspection reports