## MAC PTW 2022
MAC PTW Register - 2022
S.No. | PTW No. | Date | Activity | Company | Remarks | Expiry | Extension | Status
1 | 001/2022 MAC | 2022-01-03 | Swapping of Equipment | DU |  | 2022-01-18 |  | Closed
2 | 002/2022 MAC | 2022-01-04 | Bike Shop - Glass Installation | Graphics Hub |  | 2022-01-08 |  | Closed
3 | 003/2022 MAC | 2022-01-03 | Installing power Socket | Basil |  | 2022-01-07 |  | Closed
4 | 004/2022 MAC | 2022-01-06 | Anatomy Museum | Gemaco |  | 2022-02-06 |  | Closed
5 | 005/2022 MAC | 2022-01-07 | Sign Replacement | Mazghar Interior |  | 2022-01-17 |  | Closed
6 | 006/2022 MAC | 2022-01-14 | Pest Control | Debug- Basil |  | 2022-01-15 |  | Closed
7 | 007/2022 MAC | 2022-01-16 | Replacement of Revolving Glass | Fonoon |  | 2022-01-17 |  | Closed
8 | 008/2022 MAC | 2022-01-17 | Baynounah Lab | White Crescent |  | 2022-01-24 | 2022-02-02 | Closed
9 | 009/2022 MAC | 2022-01-17 | Epidemiology Lab | White Crescent |  | 2022-01-24 | 2022-02-02 | Closed
10 | 010/2022 MAC | 2022-01-20 | DB Modification | ME Contracting |  | 2022-01-20 |  | Closed
11 | 011/2022 MAC | 2022-01-25 | Media Façade Lighting Maintenance | CINMAR Lighting |  | 2022-01-31 |  | Closed
12 | 012/2022 MAC | 2022-01-27 | Medical Building A & B Phase 2 | White Crescent |  | 2022-02-02 | 2022-03-14 | Closed
13 | 013/2022 MAC | 2023-02-02 | Sign Board Change | Basil |  | 2022-02-02 | 2022-02-06 | Closed
14 | 014/2022 MAC | 2023-02-16 | Electrical Work | Basil |  | 2023-02-18 |  | Closed
15 | 015/2022 MAC | 2023-02-18 | Site Office Dismantling | CANAPUS |  | 2023-02-25 |  | Closed
16 | 016/2022 MAC | 2023-02-23 | DU | DU |  | 2023-03-11 |  | Closed
17 | 017/2022 MAC | 2023-02-23 | Drainage Cleaning | ADNH |  | 2023-02-24 |  | Closed
18 | 018/2022 MAC | 2023-03-10 | IBS DU Signal | DU |  | 2023-04-11 |  | Closed
19 | 019/2022 MAC | 2023-03-23 | Site Survey | Fire Stone |  | 2023-03-30 |  | Closed
20 | 020/2022 MAC | 2023-03-30 | Fit Out Work - Virology | AHI |  | 2023-04-15 | 2023-04-29 | Closed
21 | 021/2022 MAC | 2022-04-10 | BUS BAR | AL NASER |  | 2022-04-10 |  | Closed
22 | 022/2022 MAC | 2022-04-20 | Graphic Work | Graphics Hub |  | 2022-04-20 |  | Closed
23 | 023/2022 MAC | 2022-04-21 | Waterproofing | White Crescent |  | 2022-04-21 |  | Closed
24 | 024/2022 MAC | 2022-04-26 | Lab Furniture Installation | Thani Murshid |  | 2022-06-01 |  | Closed
25 | 025/2022 MAC | 2022-05-11 | Gas Relocation and Installation | ARAS MEDICAL |  | 2022-06-21 |  | Closed
26 | 026/2022 MAC | 2022-06-14 | Sprinkler Pipr Installation | Fire Stone |  | 2022-06-16 |  | Closed
27 | 027/2022 MAC | 2022-05-19 | Double Door Installation | White Crescent |  | 2022-05-23 |  | Closed
28 | 028/2022 MAC | 2022-05-23 | Brazinf of Copper Pipes | ARAS MEDICAL |  | 2022-05-26 |  | Closed
29 | 029/2022 MAC | 2022-05-13 | Sprinkler Pipr Installation (M) | Fire Stone |  | 2022-06-03 |  | Closed
30 | 030/2022 MAC | 2022-05-30 | Mini Mart | Al Eyoun Cont. LLC |  | 2022-06-30 |  | Closed
31 | 031/2022 MAC | 2022-05-30 | Installation for sticker branding on Kiosk | Royal Vision |  | 2022-05-30 |  | Closed
32 | 032/2022 MAC | 2022-06-03 | Additional Civil & MEP Reequirement in Wave Tank | Allied ME |  | 2022-06-13 | 2022-08-05 | Closed
33 | 033/2022 MAC | 2022-05-31 | Class Room Enlargment | Potenza |  | 2022-06-05 |  | Closed
34 | 034/2022 MAC | 2022-06-03 | Replacement of Wall | House of tea |  | 2022-06-06 |  | Closed
35 | 035/2022 MAC | 2022-06-07 | Digital Sign | RAMCO |  | 2022-06-14 |  | Closed
36 | 036/2022 MAC | 2022-06-09 | Fume Hood Installation | CANAPUS |  | 2022-06-20 |  | Closed
37 | 037/2022 MAC | 2022-06-15 | AP Mounting | CNS |  | 2022-06-30 |  | Closed
38 | 038/2022 MAC | 2022-06-11 | Kitchen Duct Cleaning | Blue |  | 2022-06-11 |  | Closed
39 | 039/2022 MAC | 2022-06-18 | Shut Down & Cable termination | White Crescent |  | 2022-06-18 |  | Closed
40 | 040/2022 MAC | 2022-07-12 | Wall Sticker Installation | Graphics Hub |  | 2022-07-12 |  | Closed
41 | 041/2022 MAC | 2022-07-12 | Internal Painting | Shambarg |  | 2022-09-04 |  | Closed
42 | 042/2022 MAC | 2022-07-14 | Trouble Shoot & Maint | Ankabut - Waqas |  | 2022-07-21 |  | Closed
43 | 043/2022 MAC | 2022-08-01 | Refurbishment of Flagpoles | Trident |  | 2022-08-05 |  | Closed
44 | 044/2022 MAC | 2022-08-05 | Simulated Ambulance Transfer of Equipment | Leader Healthcare |  | 2022-08-08 |  | Closed
45 | 045/2022 MAC | 2022-07-30 | Staircase Light Replacement | Potenza |  | 2022-08-02 |  | Closed
46 | 046/2022 MAC | 2022-08-03 | Ceiling Works - Dr. Shawarma | Green Palm |  | 2022-08-15 |  | Closed
47 | 047/2022 MAC | 2022-08-14 | Fire System Isolation | Fire Stone |  | 2022-08-14 |  | Closed
48 | 048/2022 MAC | 2022-11-05 | Interior Joinery Works | Gemaco |  | 2022-11-12 |  | Closed
49 | 049/2022 MAC | 2022-08-26 | Gym Equipmenr Maint | Technogym |  | 2022-08-26 |  | Closed
50 | 050/2022 MAC | 2022-08-21 | Installation of Booth, Fixing banner | Fonoon |  | 2022-08-22 |  | Closed
51 | 051/2022 MAC | 2022-08-20 | Fume Hood Work | White Crescent |  | 2022-08-20 |  | Closed
52 | 052/2022 MAC | 2022-10-14 | Topographical Survey | National Survey |  | 2022-10-17 |  | Closed
53 | 053/2022 MAC |  | Stretch Film Installation | SMART Dimension- Eurocell | for review |  |  | Posponed
54 | 054/2022 MAC | 2022-10-17 | Starbuck | Haroon |  | 2022-10-20 |  | Closed
55 | 055/2022 MAC | 2022-10-21 | Paving Tiles | Bonolota |  | 2022-11-10 |  | Closed
56 | 056/2022 MAC | 2022-10-20 | Low Calories Store- Work | OK Decoration |  | 2022-12-04 |  | Closed
57 | 057/2022 MAC | 2022-10-24 | Camera Installation- Wave Tank | Link Gulf |  | 2022-10-26 |  | Closed
58 | 058/2022 MAC | 2022-10-31 | Supply and Installation - Power Supply for Office | Holford Interior |  | 2022-12-30 |  | Closed
59 | 059/2022 MAC |  | Painting of Material Management | Potenza | MS&RA |  |  | Posponed
60 | 060/2022 MAC | 2022-11-08 | Wave Tank Snags | New Engineering |  | 2022-11-15 |  | Closed
61 | 061/2022 MAC | 2022-11-25 | KU Merchandize | Gemaco |  | 2022-11-30 |  | Closed
62 | 062/2022 MAC | 2022-12-12 | Skyline Store | Skyline |  | 2022-12-30 |  | Closed
63 | 063/2022 MAC | 2022-12-20 | PVC Tracking system Installation- Camera- at Channel | Potenza |  | 2022-12-24 |  | Closed
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88

## SAN PTW 2022
SAN PTW Register - 2022
S.No. | PTW No. | Date | Activity | Company | Remarks | Expiry | Extension | Status
1 | 001/2022 SAN | 2022-01-11 | Removal of raised floor/ ceiling/ MEP works/ Electrical/ Exhaust ducts | White Crescent | Arzanah Lab modification. | 2022-01-31 | Feb. 28, 22. | Closed
2 | 002/2022 SAN | 2022-01-11 | Removal of raised floor/ ceiling/ MEP works/ Electrical/ Exhaust ducts | White Crescent | Bu'Hassah Lab modification. | 2022-01-31 | Feb. 28, 22. | Closed
3 | 003/2022 SAN | 2022-01-13 | Arc welding for cable support. | UTC Climate, Controls & Security | B-24 & B-26 & B-31 AND B-32 at SAN Campus | 2022-01-13 |  | Closed
4 | 004/2022 SAN | 2022-01-17 | Replacement of existing chillers in hostel buildings. | UTC Climate, Controls & Security | B-24 & B-26 & B-31 AND B-32 at SAN Campus | 2022-02-07 | jun 23, 2022 | Closed
5 | 005/2022 SAN | Jan. 21, 22 | Arc welding for cable support. | UTC Climate, Controls & Security | B-32 SAN | 2022-01-22 |  | Closed
6 | 006/2022 SAN | Jan. 21, 22 | Lifting activity | White Crescent | Bu'Hassah | Jan. 24, 22 | Jan. 30, 22. | Closed
7 | 007/2022 SAN | Jan.27, 22 | New AC pipeline installation | White Crescent | Bu'Hassah | Jan. 30, 22 | Feb. 07, 22. | Closed
8 | 008/2022 SAN | Feb.01,22 | Replacement of Electrical DB/ Classes partial move modification. | AG Facilities and Contracting | SAN Buildings 1,2 & 3 | Feb. 28, 22 |  | Closed
9 | 009/2022 SAN | Feb.09,22 | Lab modification- Material delivery | PetroMiddleEast | Arzanah Lab modification. | Feb. 28, 23 |  | Closed
10 | 010/2022 SAN | Feb. 18, 2022 | MCCB installation | UTC Climate, Controls & Security | B-11, B-25 & All ATI area | March 31, 2022 | April 30, 2022 | Closed
11 | 011/2022 SAN | Feb. 18, 2022 | Haxa pod robot & exhibition item movement | Luxury movers | SAN M006 | February 20, 2022 |  | Closed
12 | 012/ 2022 SAN | Feb. 28, 2022 | Lab modification- Gas line laying and climbing | PetroMiddleEast | Arzanah Lab modification. | March 31, 2022 |  | Closed
13 | 013/ 2022 SAN | Feb. 28, 2022 | Lab modification- Orbital welding work | PetroMiddleEast | Arzanah Lab modification. | March 07, 2022 | April 05, 2022 | Closed
14 | 014/2022 SAN | Mar. 01, 2022 | Supply and installation of Fence, turnstile & access system | AG Facilities and Contracting | Near B-11 | March 11, 2022 |  | Closed
15 | 015/2022 SAN | Mar. 03, 2022 | Installation of serving counters, wall metal brackets for open shelves | Najim Al naseem | Buliding# 1 | March 07, 2022 | 2022-06-20 | Closed
16 | 016/2022 SAN | Mar. 14, 2022 | Replacement of existing chillers in hostel buildings. Hot Work | UTC Climate, Controls & Security | B-24 & B-26 & B-31 AND B-32 at SAN Campus | 2022-03-21 | 2022-05-31 | Closed
17 | 017/2022 SAN | Mar. 22, 2022 | Fire isolation permit required for Room 8326 | White Crescent | Building 8,8326 | 2022-03-21 |  | Closed
18 | 018/2022 SAN | Mar. 23, 2022 | Demolishing and Debris Removal | PetroMiddleEast | Arzanah cylinder storage room modification at service block. | April 12, 2022 |  | Closed
19 | 019/2022 SAN | Apr. 06, 2022 | Site preparation for solar ECOzy villa reassale | Bonolata | Football field, SAN campus | 2022-06-15 |  | Closed
20 | 020/2022 SAN | Apr. 06, 2022 | Lifting activity | White Crescent | Bu'Hassah | 2022-04-08 |  | Closed
21 | 021/2022 SAN | Apr. 21, 2022 | Renovation works in Gym | Qasr Al Alnaya | Satah 1st floor gym | 2022-04-30 |  | Closed
22 | 022/2022 SAN | Apr. 21, 2022 | site survey and civil work | Fire stone | SAN Campus outside airea | 2022-06-24 | 2022-07-25 | Closed
23 | 023/2022 SAN | 2022-05-09 | Lifiting by Crain | White Crescent | arzna | 2022-05-10 | May 13, 2022 | Closed
24 | 024/2022 SAN | May. 12, 2022 | The execution of classroom enlargement work | Potenza | Building 4- 4008, 4010, 4013, 4020, 4022, 4106, 4110, 4120, 4122 & 4124 | 2022-06-11 | 2022-12-31 | Closed
25 | 025/ 2022 SAN | May. 12, 2022 | Civil/ MEP work for hazardous waste room | Potenza | Building 3- 3021 a | 2022-06-11 | 2022-12-20 | Closed
26 | 026/2022 SAN | 2022-05-12 | U channel Welding | White Crescent | Arzanah | 2022-05-19 |  | Closed
27 | 027/2022 SAN | May. 17, 22 | Installation of wind tunnel | Aerolab | SAN Wind tunnel | 2022-06-16 |  | Closed
28 | 028/2022 SAN | May. 19, 22 | install cofe shop counter | MAST Solution fit out LLC | Building 3 | 2022-05-31 |  | Closed
29 | 029/2022 SAN | May. 19, 22 | install a shop | high Range | student center | 2022-07-06 |  | Closed
30 | 030/ 2022 SAN | May. 20, 22 | Lab modification- Orbital welding work | PetroMiddleEast | Arzanah Lab modification. | 2022-05-28 | 2022-06-28 | Closed
31 | 031/ 2022 SAN | May. 27, 22 | sprinkular pipe instulation | Fire stone | satah , umm saif, zarkuh | 2022-06-27 | 2022-09-15 | Closed
32 | 032/ 2022 SAN | June 10, 2022 | Supply and Installation of the Trespa Worktop. | THANI MURSHID EST. | Arzanah | 2022-06-20 |  | Closed
33 | 033/ 2022 SAN | June 15, 2022 | EECOVILLA Building and Installation | BK MODULAR | SAN ECOVILLA ZY SITE | 2022-06-30 |  | Closed
34 | 034/ 2022 SAN | June 17, 2022 | Replacement of existing chiller | UTC Climate, Controls & Security | Building 25 & ATI | 2022-07-04 | 2022-11-30 | Closed
35 | 035/ 2022 SAN | 2022-07-01 | Replacement of existing chiller | UTC Climate, Controls & Security | Building 25 & ATI | 2022-07-08 | 2023-01-16 | Closed
36 | 036/ 2022 SAN | 2022-07-05 | Painting of walls | Shambarg | All male accommodations & Classrooms | 2022-08-05 |  | Closed
37 | 038/ 2022 SAN | 2022-07-13 | kitchen hood work | high Range | Food Court area | 2022-07-20 |  | Closed
38 | 039/ 2022 SAN | 2022-07-18 | Supply and instulation of car parking | AG Facilities and Contracting | Arzanah -SAN campus | 2022-08-15 | 2022-09-05 | Closed
39 | 040/ 2022 SAN | 2022-07-19 | installing new chairs | MAST Solution fit out LLC | Building 3,2nd floor | 2022-07-25 | 2022-08-27 | Closed
40 | 041/ 2022 SAN | 2022-07-22 | BMS upgrade | honeywell | Building 3 | 2022-08-25 | 2022-11-24 | Closed
41 | 042/ 2022 SAN | 2022-07-22 | Waterproofing at Roof | White Crescent | Arzanah | 2022-07-25 | 2023-03-31 | Open
42 | 043/ 2022 SAN | Aug. 01, 22 | Spools lifting and assembly | ATD | Arzanah, lab 8028 | 2022-08-05 |  | Closed
43 | 044/ 2022 SAN | Aug. 01, 22 | Spools& support modification- Hotwork | ATD | Arzanah, lab 8028 | 2022-08-05 |  | Closed
44 | 045/ 2022 SAN | Aug. 03, 22 | changing the clocks | Smart vision | bulding 3 | 2022-08-26 |  | Closed
45 | 046/ 2022 SAN | Aug. 10, 22 | Development of Parking slots, extend internal | AJAD FM | Parking A & B located near Umm shaif behind, Zarkouh and Parking C front of ADRIC | 2022-09-30 |  | Closed
46 | 047/ 2022 SAN | Aug. 12, 22 | Replacement of Interlock Tiles for Road and Walkway at KU SAN Campus | Bonolata | Premises of Arzanah, Umm Shaif, Mosque, Habsan and Ruwais building | 2022-09-11 |  | Closed
47 | 048/ 2022 SAN | Aug. 18, 22 | Installation of Turnstile & ACS on Zarkuh, Bu Hasa, and Ruwais buildings | Emirates Link group LLC | Zarkuh, Bu Hasa, and Ruwais buildings turnstile installation | 2022-08-18 |  | Closed
48 | 049/ 2022 SAN | 2022-09-01 | supply and installation of socets | AG Facilities and Contracting | Building 3 | 2022-09-08 |  | Closed
49 | 050/ 2022 SAN | 2022-09-06 | INSTALLATION & DELIVERY | CHRISTIAN RAUN TECHNICAL | #8322 AZANEH | 2022-09-06 |  | Closed
50 | 051/ 2022 SAN | 2022-09-10 | Supply and Installation of the Power Supply for Office Relocation & Electrical work | HOLFORD Co | Arzanah Building | Oct 12.2022 | April 30, 2022 | Open
51 | 052/ 2022 SAN | 2022-09-16 | Glovebox Facility Lab 8028A Modification works. | Potenza Electro Mechanical Works LLC | Arzanah Building | 2022-10-16 | Dec. 31, 2022 | Closed
52 | 053/ 2022 SAN | 2022-09-16 | banimarie and chiller | Emirates facilites supply | Building 5 & 7 | 2022-10-19 |  | Closed
53 | 054/ 2022 SAN | 2022-09-17 | Tools related with removal and reinstall of parking structure, painting and shed installation. | Bonolata General Contracting LLC | Near Gate 1 at KU SAN Campus | 2022-10-25 |  | Closed
54 | 055/2022 SAN | Sept. 22, 2022 | carpentry and installation of sing | best cub cafe | ADNOC hostels | Oct. 01, 2022 |  | Closed
55 | 056/2022 SAN | Sept. 30, 2022 | Gas & Vacuum Line laying and suppporting | PME | 8138 gas supplier | Oct. 10, 2022 | Nov. 30, 2022 | Closed
56 | 057/2022 SAN | Oct. 5, 2022 | Central Battery System Upgradation. | SIBCA | Arzanah GF BMS room | Oct. 15, 2023 | Oct. 31, 2022 | Closed
57 | 058/2022 SAN | Oct. 10, 2022 | cable pulling | INTERNETWORK TECHNOLOGY | BULDING 1,2,3 | 2022-10-13 |  | Closed
58 | 059/ 2022 SAN | Oct. 18, 2022 | Electrical work at high-pressure combustion test center (No live line work) | ATD | Arzanah Lab 8028 combustion rig installation | 2022-10-21 |  | Closed
59 | 060/ 2022 SAN | Oct. 25, 2022 | Fit-out Works for Costa Coffee and re-location from existing location |  | Costa Coffee bulding #2 | 2022-12-20 |  | Closed
60 | 061/ 2022 SAN | Oct. 31, 2022 | Grease trap, shelves & Fix new pipe | Penguin Kitchen Equipment Installation | ADNOC hostels, Block B | 2022-11-04 |  | Closed
61 | 062/ 2022 SAN | Nov. 1, 2022 | Service visit for the Installation and Commissioning of SUNTEST XXL+ Light Exposure and Weathering testing instrument. | BCL |  |  |  | Closed
62 | 063/ 2022 SAN | Nov. 10, 2022 | Building fenced shading structure and all work related to power to it, at KU Arzanah Campus | Zero Carbon Ventures | Zero carbon project facility construction outside the building. | 10.12.22 |  | Closed
63 | 064/ 2022 SAN | Nov. 14, 2022 | Installation of gasifier pilot plant. | Sai-Tech Industries FZCO | Gasifier lab | 2022-11-30 |  | Open
64 | 065/ 2022 SAN | Nov. 14, 2022 | Sewage wate sampling from Manhole | Aces | Outside SAN boundary |  |  | Closed
65 | 066/ 2022 SAN | Nov. 18, 2022 | Removal and installation of stickers | Viola Outdoor | Replacing the Habshan outside stickers | 2022-11-27 | 3rd Jan, 2023 | Closed
66 | 067/2022 SAN | 2022-12-07 | Civil foundation for Pump and watering | ATD | Arzanah Lab 8028 combustion rig installation | 2022-12-15 |  | Open
67 | 068/2022 SAN | 2022-12-08 |  |  |  | 2022-12-16 |  | Open
68 | 069/2022 SAN | 2022-12-14 | Removing scrap | Advance scrap tr LLC | B 25-24-31 | 2022-12-25 |  | Open
69 | 070/2022 SAN | 2022-12-15 | cable pulling & instolling cameras | INTERNETWORK TECHNOLOGY | B 3 - 2 | 2022-12-22 |  | Closed
70 | 071/2022 SAN | 2022-12-15 | moving furneture | luxury logisyics | All SAN buldingS | 2022-01-16 |  | Closed
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88

## MCC PTW 2022
MCC PTW Register - 2022
S.No. | PTW No. | Date | Activity | Company | Remarks | Expiry | Extension | Status
1 | 001/2022 MCC | 2022-03-08 | PCM filling | Azelio | Furnace use | 2022-03-18 |  | Closed
2 | 002/2022 MCC | Mar. 15, 22 | HTF filling | Azelio | Sodium already inside the system. Automated functioning. | Mar. 22, 22 |  | Closed
3 | 003/2022 MCC | Mar. 23, 2022 | Lifting of smeltary & container | Azelio | MISP project | Mar. 23, 22 |  | Closed
4 | 004/2022 MCC | Mar. 23, 2022 | Lifting by crane | Azelio | MISP project | Mar. 23, 22 |  | Closed
5 | 005/2022 MCC | Aug.25, 2022 | Lifting and unloading container | Azelio | MISP project | Aug. 28, 22 |  | Closed
6 | 006/2022 MCC | Aug.29, 2022 | Lifting and unloading container | Azelio | MISP project | Aug. 30, 22 |  | Closed
7 | 007/2022 MCC | Sept. 21, 2022 | Drilling using manlift | Wahaj solar | Wahaj solar project at MISP | Sept. 23, 2022 |  | Closed
8 | 008/2022 MCC | Oct. 17, 2022 | Cleaning process for the concentrator | Wahaj solar | Wahaj solar project at MISP | Oct. 18, 2022 |  | Closed
9 | 009/2022 MCC | Oct. 19, 2022 | Unloading of aluminum furnace from container, remove the TES POD unit and replace with a new one | Azelio | Crane use | Oct. 19, 2022 |  | Closed
10 | 010/2022 MCC | Oct. 28, 2022 | Cleaning process for the concentrator | Wahaj solar | Wahaj solar project at MISP | Oct. 31, 2022 |  | Closed
11 | 011/2022 MCC | Nov. 14, 2022 | Cleaning process for the concentrator | Wahaj solar | Wahaj solar project at MISP | Nov. 14, 2022 |  | Closed
12 | 012/ 2022 MCC | Dec. 5, 2022 | Shifting the existing control room with utilities to new location | Wahaj solar | Wahaj solar project at MISP | Dec.09, 2022 |  | Closed
13 | 013/ 2022 MCC | Dec. 6, 2022 | Construction of Electrical Room | B.C.C | Azelio Project | Dec. 23, 2022 | Jan. 31, 2023 | Closed
14 | 014/2022 MCC | Dec. 12, 2022 | Cleaning process for the concentrator | Wahaj solar | Wahaj solar project at MISP | Dec. 13, 2022 | Jan. 31, 2023 | Closed
15 | 015/2022 MCC | Dec. 21, 2022 | Construction of EXECUTIVE SECURITY CABIN | GREEN PREFAB FZE | MISP project | Dec. 31, 2022 |  | Closed
16 | 016/2022 MCC | Dec. 26, 2022 | PCM filling | Azelio | Furnace use | Dec. 31, 2022 |  | Closed
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88