## Lab A02006
Lab: A02006 Lab custodian: Ms. Sara Bawasir ¦ EHS: Roberto ¦ Facilities:
S.N. | Action/ Items required | Required- Yes/ No | Responsible | Due date | Status | STATUS
General | [5 empty] | Open
1 | Agree the action/ items completion date |  | All |  |  | Close
Emergency Equipment | [5 empty] | N/A
2 | Emergency Exit Sign (Illuminated) | Yes | Facilities |  | Close
3 | DCP fire extinguisher (Class A, B, C fire) | Yes | Facilities |  | Close
4 | Metal fire extinguisher (Class D fire) if applicable | No | Facilities |  | N/A
5 | Flammable gas detector | No | Facilities |  | N/A
6 | Toxic gas detector | No | Facilities |  | N/A
7 | Oxygen detector | No | Facilities |  | N/A
8 | Eyewash station and Emergency shower - ( Emegency Eyewash available) | Yes | Facilities |  | Close
9 | Spill kit | Yes | Lab custodian/ EHS |  | Open
Identify the Designate Location for
10 | First Aid Box | Yes | Facilities/ EHS |  | Close
11 | Hazardous waste collection point | Yes | Lab custodian/ EHS |  | Close
12 | SDS, Risk Assessment & other Safety documents | Yes | Lab custodian/ EHS |  | Open
13 | Fire extinguisher | Yes | Facilities/ EHS |  | Close
14 | Spill kit | No | Lab custodian/ EHS |  | N/A
15 | General, Chemical & Sharps bins | Yes | Lab custodian/ EHS |  | Open
16 | Chemical cabinets | No | Lab custodian/ EHS |  | N/A
17 | Gas cabinets | No | Facilities |  | N/A
18 | Fume hoods/ BSC | Yes | Lab custodian/ EHS |  | Open
19 | Personal Protective Equipment & Lab coat hanger | Yes | Lab custodian/ EHS |  | Open
Ensure Ventilation requirement
20 | Laboratory ventilation - 4- 12 room air changes/hour (OSHA 29 CFR 1910.1450C) | Yes | Facilities |  | Open
21 | Gas cabinet ventilation- face velocity 150- 200 fpm at the access window open area (NFPA 55 Section 6.17.2.2) | No | Facilities |  | N/A
22 | Fume hood ventilation- face velocity 80 to 120 fpm (NFPA 45 Section A6.4.6)/BSC | No | Facilities |  | N/A
23 | Equipment exhaust ventilation- Refer equipment manual | No | Lab custodian |  | N/A
Make sure Commissioning conducted for
24 | Emergency Eyewash & Safety Shower | Yes | Facilities |  | Open
25 | Fume hoods, Laminar flow & Biosafety cabinets | Yes | Facilities |  | Open
26 | Gas detectors | No | Facilities |  | N/A
27 | Gas cabinets | No | Lab custodian |  | N/A
Documents/ Signage/ Services required
28 | Lab information notice | Yes | Lab custodian/ EHS |  | Close
29 | RACE sign | Yes | EHS |  | Open
30 | First Aiders information notice | Yes | Lab custodian |  | Open
31 | Emergency numbers | Yes | EHS |  | Open
32 | Fire extinguisher test tags | Yes | Facilities |  | Open
33 | Lab Specific Risk Register | Yes | Lab custodian |  | Open
34 | Task Specific Risk Register for individual equipment operation/ process | Yes | Lab custodian |  | Open
35 | Equipment training record | Yes | Lab custodian |  | Open
36 | Safety Data Sheets for Chemicals & Gases | Yes | Lab custodian |  | Open
37 | Chemical/ Gases inventory (online) | Yes | Lab custodian |  | Open
38 | Emergency eyewash self inspection tags | Yes | Lab custodian/ EHS |  | Open
39 | Emergency eyewash & Safety Shower inspection tags | No | Facilities |  | N/A
40 | Gas cylinder status label | No | Lab custodian/ EHS |  | N/A
41 | Secondary container label | Yes | Lab custodian/ EHS |  | Open
42 | Lab Equipment calibration & servicing | Yes | Lab custodian |  | Open
43 | Lab specific hazard signage | No | Lab custodian |  | N/A
Lab access requirements
44 | General Lab Safety Trainings | Yes | Lab user/ Lab custodian/ EHS |  | Open
45 | User Lab Specific Safety Trainings | Yes | Lab user/ Lab custodian |  | Open
46 | User access card activation | Yes | Lab user/ Lab custodian/ Security |  | Open
Hazardous material management requirements
47 | Fume hood | No | Facilities |  | N/A
48 | Chemical resistant workbench | Yes | Facilities |  | Close
49 | Personal Protective Equipment | Yes | Lab custodian |  | Open
50 | Chemical containers | No | Lab custodian |  | N/A
51 | Chemical labels | Yes | Lab custodian |  | Open
52 | Safety Data Sheets | Yes | Lab custodian |  | Open
53 | Task specific Risk Assessment | Yes | Lab custodian |  | Open
54 | Spill Kit ( Chemical - Biohazard Spill kit to be added) | No | Lab Custodian/EHS |  | N/A
55 | Corrosive cabinet for acids and bases | No | Facilities |  | N/A
56 | Flammables storage cabinet for solvents | No | Facilities |  | Open
57 | Flame arrester for ventilated flammable chemicals storage cabinet | No | Facilities |  | N/A
58 | Toxic/ noxious chemical cabinet (Ventilated) | No | Facilities |  | N/A
59 | Cabinet for low hazard solid chemicals storage | No | Facilities |  | N/A
60 | Special storage requirement | No | Lab custodian |  | N/A
61 | Flammable gas cylinder storage cabinet for flammable gases | No | Facilities |  | N/A
62 | Toxic gas cabinet for health hazard gases | No | Facilities |  | N/A
63 | Secondary containments for liquid chemicals | Yes | Lab custodian |  | Open
64 | Hazardous waste bottles for liquid waste | No | Lab custodian |  | N/A
65 | Secondary containment for hazardous waste bottles | No | Lab custodian |  | N/A
66 | Hazardous waste bin with liner for chemical solid waste | Yes | Lab custodian |  | Open
67 | Gas cylinder stands | No | Facilities |  | N/A
68 | Conduct emergency eyewash monthly self inspection | Yes | Lab custodian |  | Open
69 | Conduct emergency eyewash & safety shower regular inspection | No | Facilities |  | N/A
70 | Chemicals & Gas cylinders are below the Maximum Allowable Quantity as per Appendix-1 | Yes | Lab custodian |  | Close
Radiation Safety requirements
71 | Identify the lab is using Radioactive materials/ Radiation Producing Equipment/ Nuclear Materials | No | Lab custodian |  | N/A
72 | Make sure the RM/ RPE/ NM registered with FANR | No | Lab custodian/ EHS/ RPO |  | N/A
73 | Make sure dosimeter reading and other required monitoring is in place | No | Lab custodian/ RPO |  | N/A
Other Safety recommendations
74 | Door with glass window (Lab inside view) | Yes | Facilities |  | Close
75 | CISCO IP phone (Communication) | NO | IT |  | N/A
EHS Note:
Civil defense approval required before full operation of the FM/contractor are coordinating with civil defense - Completed Task specific/equipment specific risk assessment to be carried out before starting the experiment. All equipment in the labs need to be installed as per the design approved by project & space planning team

## Lab A02007
Lab: A02007 Lab custodian: Ms. Sara Bawasir ¦ EHS: Roberto ¦ Facilities:
S.N. | Action/ Items required | Required- Yes/ No | Responsible | Due date | Status | STATUS
General | [5 empty] | Open
1 | Agree the action/ items completion date |  | All |  |  | Close
Emergency Equipment | [5 empty] | N/A
2 | Emergency Exit Sign (Illuminated) | Yes | Facilities |  | Close
3 | DCP fire extinguisher (Class A, B, C fire) | Yes | Facilities |  | Close
4 | Metal fire extinguisher (Class D fire) if applicable | No | Facilities |  | N/A
5 | Flammable gas detector | No | Facilities |  | N/A
6 | Toxic gas detector | No | Facilities |  | N/A
7 | Oxygen detector | No | Facilities |  | N/A
8 | Eyewash station and Emergency shower - ( Emegency Eyewash available) | Yes | Facilities |  | Close
9 | Spill kit | Yes | Lab custodian/ EHS |  | Open
Identify the Designate Location for
10 | First Aid Box | Yes | Facilities/ EHS |  | Close
11 | Hazardous waste collection point | Yes | Lab custodian/ EHS |  | Close
12 | SDS, Risk Assessment & other Safety documents | Yes | Lab custodian/ EHS |  | Open
13 | Fire extinguisher | Yes | Facilities/ EHS |  | Close
14 | Spill kit | No | Lab custodian/ EHS |  | N/A
15 | General, Chemical & Sharps bins | Yes | Lab custodian/ EHS |  | Open
16 | Chemical cabinets | No | Lab custodian/ EHS |  | N/A
17 | Gas cabinets | No | Facilities |  | N/A
18 | Fume hoods/ BSC | Yes | Lab custodian/ EHS |  | Open
19 | Personal Protective Equipment & Lab coat hanger | Yes | Lab custodian/ EHS |  | Open
Ensure Ventilation requirement
20 | Laboratory ventilation - 4- 12 room air changes/hour (OSHA 29 CFR 1910.1450C) | Yes | Facilities |  | Open
21 | Gas cabinet ventilation- face velocity 150- 200 fpm at the access window open area (NFPA 55 Section 6.17.2.2) | No | Facilities |  | N/A
22 | Fume hood ventilation- face velocity 80 to 120 fpm (NFPA 45 Section A6.4.6)/BSC | No | Facilities |  | N/A
23 | Equipment exhaust ventilation- Refer equipment manual | No | Lab custodian |  | N/A
Make sure Commissioning conducted for
24 | Emergency Eyewash & Safety Shower | Yes | Facilities |  | Open
25 | Fume hoods, Laminar flow & Biosafety cabinets | Yes | Facilities |  | Open
26 | Gas detectors | No | Facilities |  | N/A
27 | Gas cabinets | No | Lab custodian |  | N/A
Documents/ Signage/ Services required
28 | Lab information notice | Yes | Lab custodian/ EHS |  | Close
29 | RACE sign | Yes | EHS |  | Open
30 | First Aiders information notice | Yes | Lab custodian |  | Open
31 | Emergency numbers | Yes | EHS |  | Open
32 | Fire extinguisher test tags | Yes | Facilities |  | Open
33 | Lab Specific Risk Register | Yes | Lab custodian |  | Open
34 | Task Specific Risk Register for individual equipment operation/ process | Yes | Lab custodian |  | Open
35 | Equipment training record | Yes | Lab custodian |  | Open
36 | Safety Data Sheets for Chemicals & Gases | Yes | Lab custodian |  | Open
37 | Chemical/ Gases inventory (online) | Yes | Lab custodian |  | Open
38 | Emergency eyewash self inspection tags | Yes | Lab custodian/ EHS |  | Open
39 | Emergency eyewash & Safety Shower inspection tags | No | Facilities |  | N/A
40 | Gas cylinder status label | No | Lab custodian/ EHS |  | N/A
41 | Secondary container label | Yes | Lab custodian/ EHS |  | Open
42 | Lab Equipment calibration & servicing | Yes | Lab custodian |  | Open
43 | Lab specific hazard signage | No | Lab custodian |  | N/A
Lab access requirements
44 | General Lab Safety Trainings | Yes | Lab user/ Lab custodian/ EHS |  | Open
45 | User Lab Specific Safety Trainings | Yes | Lab user/ Lab custodian |  | Open
46 | User access card activation | Yes | Lab user/ Lab custodian/ Security |  | Open
Hazardous material management requirements
47 | Fume hood | No | Facilities |  | N/A
48 | Chemical resistant workbench | Yes | Facilities |  | Close
49 | Personal Protective Equipment | Yes | Lab custodian |  | Open
50 | Chemical containers | No | Lab custodian |  | N/A
51 | Chemical labels | Yes | Lab custodian |  | Open
52 | Safety Data Sheets | Yes | Lab custodian |  | Open
53 | Task specific Risk Assessment | Yes | Lab custodian |  | Open
54 | Spill Kit ( Chemical - Biohazard Spill kit to be added) | No | Lab Custodian/EHS |  | N/A
55 | Corrosive cabinet for acids and bases | No | Facilities |  | N/A
56 | Flammables storage cabinet for solvents | No | Facilities |  | Open
57 | Flame arrester for ventilated flammable chemicals storage cabinet | No | Facilities |  | N/A
58 | Toxic/ noxious chemical cabinet (Ventilated) | No | Facilities |  | N/A
59 | Cabinet for low hazard solid chemicals storage | No | Facilities |  | N/A
60 | Special storage requirement | No | Lab custodian |  | N/A
61 | Flammable gas cylinder storage cabinet for flammable gases | No | Facilities |  | N/A
62 | Toxic gas cabinet for health hazard gases | No | Facilities |  | N/A
63 | Secondary containments for liquid chemicals | Yes | Lab custodian |  | Open
64 | Hazardous waste bottles for liquid waste | No | Lab custodian |  | N/A
65 | Secondary containment for hazardous waste bottles | No | Lab custodian |  | N/A
66 | Hazardous waste bin with liner for chemical solid waste | Yes | Lab custodian |  | Open
67 | Gas cylinder stands | No | Facilities |  | N/A
68 | Conduct emergency eyewash monthly self inspection | Yes | Lab custodian |  | Open
69 | Conduct emergency eyewash & safety shower regular inspection | No | Facilities |  | N/A
70 | Chemicals & Gas cylinders are below the Maximum Allowable Quantity as per Appendix-1 | Yes | Lab custodian |  | Close
Radiation Safety requirements
71 | Identify the lab is using Radioactive materials/ Radiation Producing Equipment/ Nuclear Materials | No | Lab custodian |  | N/A
72 | Make sure the RM/ RPE/ NM registered with FANR | No | Lab custodian/ EHS/ RPO |  | N/A
73 | Make sure dosimeter reading and other required monitoring is in place | No | Lab custodian/ RPO |  | N/A
Other Safety recommendations
74 | Door with glass window (Lab inside view) | Yes | Facilities |  | Close
75 | CISCO IP phone (Communication) | NO | IT |  | N/A
EHS Note:
Civil defense approval required before full operation of the FM/contractor are coordinating with civil defense - Completed Task specific/equipment specific risk assessment to be carried out before starting the experiment. All equipment in the labs need to be installed as per the design approved by project & space planning team

## Lab A02008
Lab: A02008 Lab custodian: Ms. Sara Bawasir ¦ EHS: Roberto ¦ Facilities:
S.N. | Action/ Items required | Required- Yes/ No | Responsible | Due date | Status | STATUS
General | [5 empty] | Open
1 | Agree the action/ items completion date |  | All |  |  | Close
Emergency Equipment | [5 empty] | N/A
2 | Emergency Exit Sign (Illuminated) | Yes | Facilities |  | Close
3 | DCP fire extinguisher (Class A, B, C fire) | Yes | Facilities |  | Close
4 | Metal fire extinguisher (Class D fire) if applicable | No | Facilities |  | N/A
5 | Flammable gas detector | No | Facilities |  | N/A
6 | Toxic gas detector | No | Facilities |  | N/A
7 | Oxygen detector | No | Facilities |  | N/A
8 | Eyewash station and Emergency shower - ( Emegency Eyewash available) | Yes | Facilities |  | Close
9 | Spill kit | Yes | Lab custodian/ EHS |  | Open
Identify the Designate Location for
10 | First Aid Box | Yes | Facilities/ EHS |  | Close
11 | Hazardous waste collection point | Yes | Lab custodian/ EHS |  | Close
12 | SDS, Risk Assessment & other Safety documents | Yes | Lab custodian/ EHS |  | Open
13 | Fire extinguisher | Yes | Facilities/ EHS |  | Close
14 | Spill kit | No | Lab custodian/ EHS |  | N/A
15 | General, Chemical & Sharps bins | Yes | Lab custodian/ EHS |  | Open
16 | Chemical cabinets | No | Lab custodian/ EHS |  | N/A
17 | Gas cabinets | No | Facilities |  | N/A
18 | Fume hoods/ BSC | Yes | Lab custodian/ EHS |  | Open
19 | Personal Protective Equipment & Lab coat hanger | Yes | Lab custodian/ EHS |  | Open
Ensure Ventilation requirement
20 | Laboratory ventilation - 4- 12 room air changes/hour (OSHA 29 CFR 1910.1450C) | Yes | Facilities |  | Open
21 | Gas cabinet ventilation- face velocity 150- 200 fpm at the access window open area (NFPA 55 Section 6.17.2.2) | No | Facilities |  | N/A
22 | Fume hood ventilation- face velocity 80 to 120 fpm (NFPA 45 Section A6.4.6)/BSC | No | Facilities |  | N/A
23 | Equipment exhaust ventilation- Refer equipment manual | No | Lab custodian |  | N/A
Make sure Commissioning conducted for
24 | Emergency Eyewash & Safety Shower | Yes | Facilities |  | Open
25 | Fume hoods, Laminar flow & Biosafety cabinets | Yes | Facilities |  | Open
26 | Gas detectors | No | Facilities |  | N/A
27 | Gas cabinets | No | Lab custodian |  | N/A
Documents/ Signage/ Services required
28 | Lab information notice | Yes | Lab custodian/ EHS |  | Close
29 | RACE sign | Yes | EHS |  | Open
30 | First Aiders information notice | Yes | Lab custodian |  | Open
31 | Emergency numbers | Yes | EHS |  | Open
32 | Fire extinguisher test tags | Yes | Facilities |  | Open
33 | Lab Specific Risk Register | Yes | Lab custodian |  | Open
34 | Task Specific Risk Register for individual equipment operation/ process | Yes | Lab custodian |  | Open
35 | Equipment training record | Yes | Lab custodian |  | Open
36 | Safety Data Sheets for Chemicals & Gases | Yes | Lab custodian |  | Open
37 | Chemical/ Gases inventory (online) | Yes | Lab custodian |  | Open
38 | Emergency eyewash self inspection tags | Yes | Lab custodian/ EHS |  | Open
39 | Emergency eyewash & Safety Shower inspection tags | No | Facilities |  | N/A
40 | Gas cylinder status label | No | Lab custodian/ EHS |  | N/A
41 | Secondary container label | Yes | Lab custodian/ EHS |  | Open
42 | Lab Equipment calibration & servicing | Yes | Lab custodian |  | Open
43 | Lab specific hazard signage | No | Lab custodian |  | N/A
Lab access requirements
44 | General Lab Safety Trainings | Yes | Lab user/ Lab custodian/ EHS |  | Open
45 | User Lab Specific Safety Trainings | Yes | Lab user/ Lab custodian |  | Open
46 | User access card activation | Yes | Lab user/ Lab custodian/ Security |  | Open
Hazardous material management requirements
47 | Fume hood | No | Facilities |  | N/A
48 | Chemical resistant workbench | Yes | Facilities |  | Close
49 | Personal Protective Equipment | Yes | Lab custodian |  | Open
50 | Chemical containers | No | Lab custodian |  | N/A
51 | Chemical labels | Yes | Lab custodian |  | Open
52 | Safety Data Sheets | Yes | Lab custodian |  | Open
53 | Task specific Risk Assessment | Yes | Lab custodian |  | Open
54 | Spill Kit ( Chemical - Biohazard Spill kit to be added) | No | Lab Custodian/EHS |  | N/A
55 | Corrosive cabinet for acids and bases | No | Facilities |  | N/A
56 | Flammables storage cabinet for solvents | No | Facilities |  | Open
57 | Flame arrester for ventilated flammable chemicals storage cabinet | No | Facilities |  | N/A
58 | Toxic/ noxious chemical cabinet (Ventilated) | No | Facilities |  | N/A
59 | Cabinet for low hazard solid chemicals storage | No | Facilities |  | N/A
60 | Special storage requirement | No | Lab custodian |  | N/A
61 | Flammable gas cylinder storage cabinet for flammable gases | No | Facilities |  | N/A
62 | Toxic gas cabinet for health hazard gases | No | Facilities |  | N/A
63 | Secondary containments for liquid chemicals | Yes | Lab custodian |  | Open
64 | Hazardous waste bottles for liquid waste | No | Lab custodian |  | N/A
65 | Secondary containment for hazardous waste bottles | No | Lab custodian |  | N/A
66 | Hazardous waste bin with liner for chemical solid waste | Yes | Lab custodian |  | Open
67 | Gas cylinder stands | No | Facilities |  | N/A
68 | Conduct emergency eyewash monthly self inspection | Yes | Lab custodian |  | Open
69 | Conduct emergency eyewash & safety shower regular inspection | No | Facilities |  | N/A
70 | Chemicals & Gas cylinders are below the Maximum Allowable Quantity as per Appendix-1 | Yes | Lab custodian |  | Close
Radiation Safety requirements
71 | Identify the lab is using Radioactive materials/ Radiation Producing Equipment/ Nuclear Materials | No | Lab custodian |  | N/A
72 | Make sure the RM/ RPE/ NM registered with FANR | No | Lab custodian/ EHS/ RPO |  | N/A
73 | Make sure dosimeter reading and other required monitoring is in place | No | Lab custodian/ RPO |  | N/A
Other Safety recommendations
74 | Door with glass window (Lab inside view) | Yes | Facilities |  | Close
75 | CISCO IP phone (Communication) | NO | IT |  | N/A
EHS Note:
Civil defense approval required before full operation of the FM/contractor are coordinating with civil defense - Completed Task specific/equipment specific risk assessment to be carried out before starting the experiment. All equipment in the labs need to be installed as per the design approved by project & space planning team

## Lab A02012
Lab: A02012 Lab custodian: Ms. Sara Bawasir ¦ EHS: Roberto ¦ Facilities:
S.N. | Action/ Items required | Required- Yes/ No | Responsible | Due date | Status | STATUS
General | [5 empty] | Open
1 | Agree the action/ items completion date |  | All |  |  | Close
Emergency Equipment | [5 empty] | N/A
2 | Emergency Exit Sign (Illuminated) | Yes | Facilities |  | Close
3 | DCP fire extinguisher (Class A, B, C fire) | Yes | Facilities |  | Close
4 | Metal fire extinguisher (Class D fire) if applicable | No | Facilities |  | N/A
5 | Flammable gas detector | No | Facilities |  | N/A
6 | Toxic gas detector | No | Facilities |  | N/A
7 | Oxygen detector | No | Facilities |  | N/A
8 | Eyewash station and Emergency shower - ( Emegency Eyewash available) | Yes | Facilities |  | Close
9 | Spill kit | Yes | Lab custodian/ EHS |  | Open
Identify the Designate Location for
10 | First Aid Box | Yes | Facilities/ EHS |  | Close
11 | Hazardous waste collection point | Yes | Lab custodian/ EHS |  | Close
12 | SDS, Risk Assessment & other Safety documents | Yes | Lab custodian/ EHS |  | Open
13 | Fire extinguisher | Yes | Facilities/ EHS |  | Close
14 | Spill kit | No | Lab custodian/ EHS |  | N/A
15 | General, Chemical & Sharps bins | Yes | Lab custodian/ EHS |  | Open
16 | Chemical cabinets | No | Lab custodian/ EHS |  | N/A
17 | Gas cabinets | No | Facilities |  | N/A
18 | Fume hoods/ BSC | Yes | Lab custodian/ EHS |  | Open
19 | Personal Protective Equipment & Lab coat hanger | Yes | Lab custodian/ EHS |  | Open
Ensure Ventilation requirement
20 | Laboratory ventilation - 4- 12 room air changes/hour (OSHA 29 CFR 1910.1450C) | Yes | Facilities |  | Open
21 | Gas cabinet ventilation- face velocity 150- 200 fpm at the access window open area (NFPA 55 Section 6.17.2.2) | No | Facilities |  | N/A
22 | Fume hood ventilation- face velocity 80 to 120 fpm (NFPA 45 Section A6.4.6)/BSC | No | Facilities |  | N/A
23 | Equipment exhaust ventilation- Refer equipment manual | No | Lab custodian |  | N/A
Make sure Commissioning conducted for
24 | Emergency Eyewash & Safety Shower | Yes | Facilities |  | Open
25 | Fume hoods, Laminar flow & Biosafety cabinets | Yes | Facilities |  | Open
26 | Gas detectors | No | Facilities |  | N/A
27 | Gas cabinets | No | Lab custodian |  | N/A
Documents/ Signage/ Services required
28 | Lab information notice | Yes | Lab custodian/ EHS |  | Close
29 | RACE sign | Yes | EHS |  | Open
30 | First Aiders information notice | Yes | Lab custodian |  | Open
31 | Emergency numbers | Yes | EHS |  | Open
32 | Fire extinguisher test tags | Yes | Facilities |  | Open
33 | Lab Specific Risk Register | Yes | Lab custodian |  | Open
34 | Task Specific Risk Register for individual equipment operation/ process | Yes | Lab custodian |  | Open
35 | Equipment training record | Yes | Lab custodian |  | Open
36 | Safety Data Sheets for Chemicals & Gases | Yes | Lab custodian |  | Open
37 | Chemical/ Gases inventory (online) | Yes | Lab custodian |  | Open
38 | Emergency eyewash self inspection tags | Yes | Lab custodian/ EHS |  | Open
39 | Emergency eyewash & Safety Shower inspection tags | No | Facilities |  | N/A
40 | Gas cylinder status label | No | Lab custodian/ EHS |  | N/A
41 | Secondary container label | Yes | Lab custodian/ EHS |  | Open
42 | Lab Equipment calibration & servicing | Yes | Lab custodian |  | Open
43 | Lab specific hazard signage | No | Lab custodian |  | N/A
Lab access requirements
44 | General Lab Safety Trainings | Yes | Lab user/ Lab custodian/ EHS |  | Open
45 | User Lab Specific Safety Trainings | Yes | Lab user/ Lab custodian |  | Open
46 | User access card activation | Yes | Lab user/ Lab custodian/ Security |  | Open
Hazardous material management requirements
47 | Fume hood | No | Facilities |  | N/A
48 | Chemical resistant workbench | Yes | Facilities |  | Close
49 | Personal Protective Equipment | Yes | Lab custodian |  | Open
50 | Chemical containers | No | Lab custodian |  | N/A
51 | Chemical labels | Yes | Lab custodian |  | Open
52 | Safety Data Sheets | Yes | Lab custodian |  | Open
53 | Task specific Risk Assessment | Yes | Lab custodian |  | Open
54 | Spill Kit ( Chemical - Biohazard Spill kit to be added) | No | Lab Custodian/EHS |  | N/A
55 | Corrosive cabinet for acids and bases | No | Facilities |  | N/A
56 | Flammables storage cabinet for solvents | No | Facilities |  | Open
57 | Flame arrester for ventilated flammable chemicals storage cabinet | No | Facilities |  | N/A
58 | Toxic/ noxious chemical cabinet (Ventilated) | No | Facilities |  | N/A
59 | Cabinet for low hazard solid chemicals storage | No | Facilities |  | N/A
60 | Special storage requirement | No | Lab custodian |  | N/A
61 | Flammable gas cylinder storage cabinet for flammable gases | No | Facilities |  | N/A
62 | Toxic gas cabinet for health hazard gases | No | Facilities |  | N/A
63 | Secondary containments for liquid chemicals | Yes | Lab custodian |  | Open
64 | Hazardous waste bottles for liquid waste | No | Lab custodian |  | N/A
65 | Secondary containment for hazardous waste bottles | No | Lab custodian |  | N/A
66 | Hazardous waste bin with liner for chemical solid waste | Yes | Lab custodian |  | Open
67 | Gas cylinder stands | No | Facilities |  | N/A
68 | Conduct emergency eyewash monthly self inspection | Yes | Lab custodian |  | Open
69 | Conduct emergency eyewash & safety shower regular inspection | No | Facilities |  | N/A
70 | Chemicals & Gas cylinders are below the Maximum Allowable Quantity as per Appendix-1 | Yes | Lab custodian |  | Close
Radiation Safety requirements
71 | Identify the lab is using Radioactive materials/ Radiation Producing Equipment/ Nuclear Materials | No | Lab custodian |  | N/A
72 | Make sure the RM/ RPE/ NM registered with FANR | No | Lab custodian/ EHS/ RPO |  | N/A
73 | Make sure dosimeter reading and other required monitoring is in place | No | Lab custodian/ RPO |  | N/A
Other Safety recommendations
74 | Door with glass window (Lab inside view) | Yes | Facilities |  | Close
75 | CISCO IP phone (Communication) | NO | IT |  | N/A
EHS Note:
Civil defense approval required before full operation of the FM/contractor are coordinating with civil defense - Completed Task specific/equipment specific risk assessment to be carried out before starting the experiment. All equipment in the labs need to be installed as per the design approved by project & space planning team