## Slide 1: EHS 2022 Objectives - Meeting
EHS Department
20 DECEMBER 2022

## Slide 2: EHS Departmental Objectives-2022
S/N | Objectives Details | Updates
1 | Attain one or more new national \ International award and or certification (different than ISO9001) | KU awarded International Safety Award from British Safety Council-2022. -Newspaper clippings Distinction Trophy received . Certificate & Plaque also received KU received RoSPA Silver award-2022. Khalifa University on LinkedIn: حصلت #جامعة_خليفة على الجائزة الفضية للجمعية الملكية للوقاية من الحوادث ¦ 15 comments BSC Award Pre Audit ( Nov-22) - Completed report received indicating certain recommendations. Five Star Audit (May -23) Sword of Honor Award from British safety Council. (Sept-23)

## Slide 3: EHS Departmental Objectives-2022
S/N | Objectives Details | Updates
2 | 90% accomplishment EHS training of all KU community . | Total staff + students= 5590 Attended= 5098 (till Dec 5th,2022) Percentage completed = 91.2% ( as of Dec 5th.2022) Status: Completed
3 | Assure that 100% (minimum completion of 80% on monthly plan) of all KU portable or movable appliance/Hand-held items/Extension leads are calibrated or PAT testing conducted inline with EHS compliances. | Collected documents of current PAT test carried out in both campuses. Proceeding as per plan. Requested to unify frequency of PAT test in both campuses. Meeting organized with FM dept. and Imdaad. Status: Completed

## Slide 4: EHS Departmental Objectives-2022
S/N | Objectives Details | Updates
4 | Achieve 100% compatibility with national standards | SAN Campus & Main campus- Fire Specialist contractor M/s Sibca ( Imdaad) submitted Documents to Abu Dhabi Civil Defense and waiting for inspection date for fire prevention certificate. Status: Main Campus: Completed SAN Campus Inspection – Still pending Civil Defense approval
5 | Increase the recycle of general waste to 30% . | Meeting Held with West Coast contractor. Advised them to segregate waste from source for recycling. Status: Overall Till 30 Nov 2022- 26% (In-progress)
6 | Establish Energy Management Plan & Sustainable Practices for every facility in KU. | Actions taken: Discussion with FM Maintenance team to prepare Energy Management Plan and sustainable practices Plan. Status: Completed
7 | Target 3% reduction of Energy consumption from the base year (2019) . | Discussion with FM Maintenance team to analyze savings on initiatives taken. (As of 30 Nov -2022) Main Campus 2.03% SAN Campus 3.29% Average: 2.5%

## Slide 5: EHS Departmental Objectives-2022…. Contd.,
S/N | Objectives Details | Updates
8 | Develop on-job training plan for EHS staff targeting 30% of the department job responsibilities/resources by Feb 2022. Establish implementation to achieve 90% of the set plan. | EHS team training Needs for 2022 review in progress. Will discuss with HR training plan upon finalization. Action plan developed & started on- job training.
Major Activities | Backup
COVID Al Hosn software, communication, statistics, and process flow (Nadia) Female Accommodation Inspections (Aisha) Medical School Lab Hazards (Faris) EHS online training process flow and Dashboard (Nadia) Organizing EHS Events, Campaigns (Hend) Collection of Electricity & water Data (Hend) Food Safety – UAE standards, Hazard Identification & Inspection (Sultan) High field courses- Fire safety level-2 Simulator hands. COSHH, Food safety (Roberto) Raising PR, EHS Budget (Roberto) Identifying Unsafe Acts /Conditions (Navaz/Ahammed) Status: All completed | Hend & Aisha Nadia & Hend Roberto & Hend Aisha , Hend Aisha, Nadia Roberto, Nadia Hend, Nadia, Aisha Nadia, Sultan Hend, Sultan, Aisha ALL

## Slide 6: EHS Departmental Objectives-2022…. Contd.,
S/N | Objectives Details | Updates
9 | Complete full Integrated of Facilities Management CAFM Solution | Status: Waiting for VP Direction
10 | Develop Integrated Quality Management System and achieve ISO 9001 or more (ISO standard , APPA and RICS). | Assisting Shahul in implementation Status: Documents under review and finalization Stage 1 audit is scheduled 26-30 Dec
11 | Propose 3-5 enhanced in department policy, process & procedures to achieve time reduction, cost saving, customer satisfaction, service quality improvement..etc. | Internal EHS meeting organized . Review of existing policies, procedures and processes, not covered by CAFM system to minimize time & cost: Status: Selection of EHS Lab Excellence Award Policies and Manual have been updated
12 | Develop enhanced functional unit level responsible matrix and apply departmental DoA | RACI matrix Status :Completed
13 | Implement periodical One-to-One staff meeting with the line manager and submit the improvement action plan | Monthly meeting held and meetings recorded. Status: Completed