## Sheet1
[5 empty] | Initial Risk |  |  |  | Residual Risk |  |  | System Of Evaluation
Process | Issues / Threats Identified from SWOT | Interested parties | SOURCES OF RISK / OPPORTUNITIES (Context/Interested parties/ customer/Legal requirements) | Whether Issues Risk or Opportunities | Probability (P) | Severity (S) | Risk/Opportunities (Score) (P X S) | Control measures /Action Plan | Probability (P) | Severity (S) | Risk / Opportunities (Score)
Operations / EHSMS Process | (Other Issues related to EHSMS) : Handling / disposal of Hazardous/Non hazardous waste | External Community Legal Authorities Client | 1. Legal Authorities / requirements regarding disposal of Hazardous / Non hazardous wastes. 2. Closure of hazardous handling facility | (Opportunity) 1. Environment protection by safe handling of waste | 3 | 3 | 9 | 1. Firm contract with Reuse / Destruction of Hazardous waste through approved agency 2. Verify the license validition of 3rd party agency 3. Conducting audit and inspection | 1 | 3 | 3 | Veriifcation of Contract copy,Approved Third party waste disposal license, manifest copy. Inspection /Audits
Operations / EHSMS Process | Handling / disposal of Referigerants | External Community Legal Authorities Client | 1. Leakage of refeigerant cylinder during Dismantling / Handling / Storage | (Risk) 1. Accidental Relase of referigerant to atmosphere (Opportunity) 1. Environment protection by removing Ozone layer destruction materails | 3 | 3 | 9 | 1. Approved HSE MS Procedure for safe Handling / Disposal of referigerant Cylinder 2. Training on safe handling of cylinders to all employees inovled and Job performed only by trained and competent person. 3. Emergency handling plan to handle release of referigerants. 4.Referigerant cylinder stored in well ventilated place away from any heat source. 5. Minimizing retention time and immediate disposal of rferigerant through authorized third party or handover to client for necessary recycling. | 1 | 3 | 3 | Review of SOP relating to referigerant storage & disposal. Inspection/Auditing
Operations / EHSMS Process | (Emergency Situation) Fire / Gas leak / Chemical spillage / Unintended release of gas cylinders /Prolonged power failue | External Community Legal Authorities Client ,Civil Defense,OSHAD | 1. Legal Authorities / requirements regarding handling of emergency situation. 2. Fire detection / protection not maintained / inspected 3. Non qualifed personnels 4. Panic condition | (Risk) 1. Failure to Handling Emergency situation leading to damages / injuries. 2. Fines / improvement notice from legal authorities. | 3 | 3 | 9 | 1. Approved Emergency Plan for KU and Training to employees 2. Familirization of Emergency handling plan / procedure during site Induction. 3. Display of emergency contact information at prominent location. 4. Conduct / Participate in Regular emergency Drills organsied. 5. Display of Emergency Exit Plan 6. Maintenance for fire portection / detection system by competent personnels. | 1 | 3 | 3 | Mock drill reports
Operations / EHSMS Process | (Waste Handling) Improper disposal of waste increasing Landfill | External Community Legal Authorities Client | 1. Legal Authorities / requirements regarding segregation / disposal of waste. 2. improper segregation of waste at source 3. Lack of facility / awareness on waste management. 4. expiry of contact with waste handling agency | (Opportunity) 1. Segeregation of waste at source and reduction in landfill. 2. Recycling of waste increase revenue, reduce waste management cost. (Risk) 1. Fines due to improper waste handling 2. increase in cost of waste management. 3. loss of resources due to waste generation. | 3 | 3 | 9 | 1. Approved waste handling contract with CWM approved agencies., based on analysis on type of waste generated at site. 2. Provision of suitable training / Povision for collection / disposition of waste throuhg approved waste handling / transportation agency. 3. Regular training to employees on waste generation, reuse, recycle and reduce principles. 4. Update SOP/ Produciton methods review to reduce rejections 5. Regular measurement, Monitoring and Analysis of waste generated / recycled. | 1 | 3 | 3 | Veriifcation of Contract copy,Approved Third party waste disposal license, manifest copy. Inspection /Audits
EHSMS Process | (Other Issues related to EMS) : 1. Changes in legal requirements | External Community Legal Authorities Client ,OSHAD | 1. Legal Authorities / requirements | (Risk) 1. Fines / improvement notice from legal authorities. | 3 | 3 | 9 | 1. EHSMS Procedure "Identification of Legal and Other Requirements Procedure" 2. Regular review and Update of "EHS & Other Legal requirements register" | 1 | 3 | 3 | Constant review of legal compliance through Inspections/Audits/Management reviews.
Operations / EHSMS Process | flood / sandstorm / earthquake etc. | External Community Legal Authorities Client | 1. Natural calamities | (Risk) 1. Failure to Handling Emergency situation leading to damages / injuries. 2. Fines / improvement notice from legal authorities. | 3 | 3 | 9 | 1. Approved Emergency Plan for KU and Training to employees 2. Familirization of Emergency handling plan / procedure during site Induction. 3. Display of emergency contact information at prominent location. 4. Conduct / Participate in Regular emergency Drills organsied. 5. Display of Emergency Exit Plan 6. Maintenance for fire portection / detection system by competent personnels. | 1 | 3 | 3 | Announcements to KU community received from regulatory bodies such as NCEMA,OSHAD
Operations / EnMS Process | Energy conservation plan and implementation. | KU,ADDC,DOE | 1. Financial restrictions 2. Time consumption process 3.Manpower constarints | Risk 1. Budget cuts 2.Not meeting targets set by UAE Energy stategy 2050 /ADDC Opportunities: 1. Huge saving potential 2. Benefit for students as they can involve in students projects related to energy conservation. | 3 | 3 | 9 | 1. Mangement commitment to implement ISO 50001 2. Formation of Energy Management task force & appointment of Energy managers. 3. Training on Energy management ssytem-ISO50001 4. Policy development relating to energy conservation, water management, sustainability-etc., | 1 | 3 | 3 | Energy Inspections /audits
Operations / EHSMS Process | Improper maintenance of Safety related Building systems | External Community Legal Authorities Client (Civil defense, OSHAD, MOHAP,DOH, NCEMA,DOE) | 1. Legal Authorities / requirements regarding occupational Safety & Health. 2. improper segregation of waste at source 3. Lack of facility / awareness on H&S management. 4. expiry of fire systems contract with civil defense. | (Opportunity) 1. Benchmarking of KU EHS standards 2. Zero accidents. (Risk) 1. Fines due to improper H&S standards 2. increase in cost ofInsurance premiums 3. loss of resources due to more accidents | 3 | 3 | 9 | 1. Approved fire system contract with civil defense., 2. Provision of suitable training 3. Regular training to employees on health and safety issues 4. Update SOP/ method statements review to reduce accidents 5. Regular measurement, Monitoring and Analysis of EHS statistics | 1 | 3 | 3 | Veriifcation of validfire system Contract copy, Inspection /Audits/management review meetings.