## Sheet1
Org Unit Reporting Entity | Org Unit Name | Process Name | Risk Name | Risk Description | Risk - Inherent Risk Impact | Risk - Inherent Risk Likelihood | Risk - Inherent Risk Rating | Risk - Residual Risk Rating (Risk Assessment) | Control Name | Control Description | Risk Rating Rationalization | Control Operating Effectiveness | Procedures | Documents | Worksheet
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-01 | Lack of adequate planning, long term plan for sustainability of operations, funding requirements and detailed work plans / milestones for the projects may result in delays, inadequate monitoring and negative impact on project quality and management. | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-01 | - Detailed work plans have been developed for all ARIC projects - Qualitative KPIs are identified in the work plans and are closely monitored, however, KPIs will follow a SMART methodology. |  | Good | Review the project plans/proposal which was submitted to Top management regarding to ARIC project and verify the following: 1- The project plan/proposal for ARIC is exist and approved by the top management 2- the project plan should cover at least the following: – Detailed project schedule. – Milestones and timelines for deliverables. – Needs for personnel, funds, and non-personnel resources (such as equipment, facilities, and information). – Progress monitoring and reporting – Detailed roles and responsibilities for project staff. – Performance evaluation. | 1. Research Project Proposal | WP_1
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-02 | Absence of committees and their charter and by laws may lead to inefficiencies, errors and delays in decision making | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-02 | - Senior management board (SMB) is formed and in charge of decision making. |  | Good | 1- Check if the Senior Management Board (SMB) for ARIC project is formed and minutes are documented 2- Review whether SMB meetings consists of minimum no of members 3- Review the frequency of meetings and check SMB has met for the required no of times. | 1. Senior Management Board and MoMs | WP_2
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-03 | Inadequate management oversight over the project resulting in desired research benefits / objectives not achieved | Major | Possible | Significant Risk | Continuous Review | KU-C-ARIC-03 | - The SMB is held on periodic basis - Projects progress reports are also issued. - All meetings are minuted. |  | Good | 1- Ensure there is progress monitoring and minutes are documented from SMB 2 - Ensure compliance with the agreement 3 - Obtain the Organization structure for the ARIC center and make sure there is no shortage in staff and all approved positions are filled and org chart is approved by SMB 4- Review process of patents and publication | 1. Organization chart 2. List of Patents and Publications | WP_3
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-04 | Absence of an approved budget / budget monitoring process for the program may lead to delays, unclear project objectives and inability to monitor over / under utilizations and determine actions thereof. | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-04 | - The annual budget is shared by one of the SMB members who shares with KU Finance. - Budget vs actual will be monitored project wise. |  | Good | 1- Obtain and ensure that the budget is approved by the SMB 2- Check if there are any significant variations from the budget | 1. Approval of budget to SMB 2. Variations in the budget | WP_4
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-05 | All respective costs (costs of AHC / Strata participants in the research projects, costs of co-directors etc.) may not ne included in the budget on account of inadequate budgeting process. | Major | Possible | Significant Risk | Continuous Review | KU-C-ARIC-05 | The budget is shared by Member with KU finance. It will be reviewed against agreement clauses and unanimous approval will be taken from the SMB. |  | Good | 1- Obtain and ensure that the budget is approved by the SMB 2- Check if there are any significant variations from the budget | 1. Approval of budget to SMB 2. Variations in the budget | WP_5
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-06 | Lack of sufficient manpower dedicated for research projects such as research fellow or students ( MSc. / PhD.) may lead to non achievement of project milestones with required time | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-06 | - Required no of students are identified for each project - Graduate school is followed up for allocation of students to each project - Communication mechanism is in place with HR and Research Services for recruitment of temporary staff and their allocation to projects |  | Good | 1 - Check plan vs actual deployment of manpower and inquire for any major differences 2- Check against project plan | 1. Planned vs Actual - Staff | WP_6
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-07 | Inappropriate balance of research, admin & teaching activities may compromise the quality of the research activity. | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-07 | - Faculty handbook has identified requirement of efforts for research - Teaching requirements are reduced with appropriate approval in case faculty needs to commit extra efforts on the project |  | Good | 1 - Check approved org chart and verify any major differences i.e. unfilled positions etc. | 1. Organization chart and vacancies | WP_7
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-08 | Lack of documented and approved strategic plan, Operation plan and Key Performance Indicators | Major | Possible | Significant Risk | Continuous Review | KU-C-ARIC-08 | Qualitative Project KPIs are developed. Monthly project progress reports are issued Center KPIs are set and are monitored and reported quarterly to SMB. |  | Good | 1- Ensure that there are center level and staff level KPIs with periodic monitoring | 1. KPIs - Target vs Actuals | WP_8
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-09 | Inadequate project monitoring and reporting process may lead to project delays. | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-09 | Monthly project reports are submitted to AHC Strata/SMB Annual and Interim reports are submitted to Research Services office. |  | Good | 1- Ensure project monitoring reports are created and shared with SMB 2- Check for equipment maintenance plan 3. Review and check whether the Annual and Interim reports are submitted to Research Services Office | 1. Project Monitoring reports 2. Equipment maintenance Plan 3. Annual and Interim reports submitted to Research Services Office | WP_9
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-10 | Lack of authority matrix may negatively impact the governance and flow of operations. | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-10 | The KU Delegation of Authority Matrix is followed. |  | Good | 1. Check whether KU DoA covers the authority limits for ARIC | 1. Delegation of Authority | WP_10
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-11 | Inadequate monitoring and reporting of the contract terms and conditions may lead to non-compliance with the ARIC agreement | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-11 | The SMB meets on quarterly basis with members from KU and AHC. Monthly Progress reports are also submitted on each project. |  | Good | 1- Ensure project monitoring reposts are created and shared with SMB 2. Check whether SMB meets on a quarterly basis | 1. Project Monitoring reports 2. SMB minutes and presentation | WP_11
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-12 | Lack of adequate policies and procedures may lead to negative impact of project completion, inadequate operations, and negative financial impacts. | Major | Possible | Significant Risk | Continuous Review | KU-C-ARIC-12 | Separate Procedures / Workflows are not documented. Only KU policies and Procedures are followed |  | Good | 1. Check whether procedures and workflows are documented and review whether the procedures are complied. | 1. Policies and Procedures | WP_12
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-13 | Lack of periodic performance review of SMB effectiveness may result in non-achievement of set goals / targets | Moderate | Possible | Moderate Risk | No Major Concern | KU-C-ARIC-13 | The SMB meets on periodic basis. The key issues are discussed, addressed and minuted in every meeting. |  | Good | 1- Check if the Senior Management Board (SMB) for ARIC project is formed and minutes are documented 2- Review whether SMB meetings consists of minimum no of members 3- Review the frequency of meetings and check SMB has met for the required no of times. | 1. SMB - MoMs | WP_13
* None Selected | KU | Aerospace/Advanced Research and Innovation Center | KU-ARIC-14 | Lack of ownership rights of intellectual property in employees contracts and confidentiality / security of the outcome of research activities may lead to data and information breaches. | Major | Possible | Significant Risk | Continuous Review | KU-C-ARIC-14 | Ownership rights of intellectual property are included in all employees contracts. |  | Good | 1. Check whether the ownership of IP are included in all employee contracts | 1. Employee contracts | WP_14
* No fraud risks available for ARIC as per the KU Fraud Risk Register