# Manufacturing of B-777/787 Ribs using Thermoplastic Composites

# Dr. Sanjeev Rao

| Project PI: Sanjeev Rao Department: Khalifa University | Checked by: Wesley Cantwell Department: ARIC |
| --- | --- |
| Approved by: ARIC SMB Date of meeting: 20th January 2021 |  |

# Project definition

The primary purpose of this work is to redesign the manufacturing process of Boeing 777/787 ribs for engineering thermoplastic materials that satisfy BMS requirements as primary structure. It will contribute to STRATA’s immediate requirement to demonstrate the capability of manufacturing thermoplastic composites aircraft structures, in effect creating local UAE national talent pool to choose from for the upcoming projects. It will contribute to ARIC's mission through the development and application of knowledge and by improving the international visibility of scientific research in the UAE. Moreover, the envisaged research is consistent with the focus sectors of “Aviation, Aerospace and Defence” and “Transportation, Trade, & Logistics” specifically identified in the Abu Dhabi 2030 vision as important for the economic diversification of Abu Dhabi.

# Objectives

- Develop capabilities to manufacture thermoplastic aircraft ribs

- Develop research capabilities to address and mitigate manufacturing associated issues

- Contribute to the process of Emiratization

# Approach

## A building block approach is used in this work. The work envisaged in this proposal is divided into six work packages, each of which consisting of a number of tasks. For each work package a description of the methods used to accomplish each task is provided followed by a table that summarizes key information about the work package, such as the lead researcher, its duration, the required human resources, and the expected outcomes and deliverables.

# Expected deliverables

Working finite element model with processing recommendations.

Tool design and one rigid tooling.

Product demonstrator.

Mid to high TRL manufacturing system (semi or fully automated).

# Resources

- Sanjeev Rao (10%) – KU  (PI)

- Wesley Cantwell (10%) – KU

- Imad Barsoum (5%)– KU

- Alia Aziz (100%) – KU

- Mohamed Mehdi Alkrunz (100%) – KU

- Pradeep George (30%) – KU

- Strata Engineering support AED 200,000

# Gantt Chart or Timeline

| Tasks & Activities |  | Period 1 | Period 2 |  | Period 3 |  | Period 4 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q4 | Q1/Q2 | Q3/Q4 | Q1/Q2 | Q3/Q4 | Q1/ Q2 | Q3 |
|  |  | 2019 | 2020 |  | 2021 |  | 2022 |  |
| WP 1: Material selection |  |  |  |  |  |  |  |  |
| 1 | Material selection |  | 100% complete |  |  |  |  |  |
| 2 | Structural requirements |  |  |  | 100% complete |  |  |  |
| 3 | Coupon testing |  |  |  | 100% complete |  |  |  |
| 4 | Allowables |  |  |  | 100% completed via DoE |  |  |  |
| WP 2: Process simulation |  |  |  |  |  |  |  |  |
| 1 | Model generation |  |  |  |  |  |  |  |
| 2 | Single curvature tests |  |  |  |  | In-progress |  |  |
| 3 | Double curvature tests |  |  |  |  |  | Redundant |  |
| WP 3: Tooling |  |  |  |  |  |  |  |  |
| 1 | Design |  |  | 100% complete, original design provided by Strata |  |  |  |  |
| 2 | Material selection |  |  | 100% complete |  |  |  |  |
| 3 | Simulation |  |  |  | In-progress |  |  |  |
| 4 | Prototype |  |  |  |  | In-progress |  |  |
| 5 | Final tool |  |  |  |  |  | In-progress |  |
| WP 4: Prototype |  |  |  |  |  |  |  |  |
| 1 | RVE generation |  |  |  |  |  | In-progress |  |
| 2 | RVE manufacturing |  |  |  |  |  | In-progress |  |
| 3 | RVE material forming |  |  |  |  |  |  |  |
| 4 | Testing |  |  |  |  |  |  |  |
| WP 5: Bonding |  |  |  |  |  |  |  |  |
| 1 | Ultrasonic welding |  |  |  |  |  |  |  |
| 2 | Ultrasonic stacking |  |  |  |  |  |  |  |
| 3 | Resistance welding |  |  |  |  |  |  |  |
| 4 | Co-consolidation |  |  |  |  |  |  |  |
| WP 6: Prototype |  |  |  |  |  |  |  |  |
| 1 | Ribs forming |  |  |  |  |  |  |  |
| 2 | Iso-grids |  |  |  |  |  |  |  |
| 3 | Secondary bonding |  |  |  |  |  |  |  |
| 4 | Testing |  |  |  |  |  |  |  |

# Estimated budget inc. all costs.

- Alia Aziz (100%) – KU

- Mohamed Mehdi Alkrunz (100%) – KU

- Pradeep George (30%) – KU

- Materials and consumables: AED 200,000

# Equipment requirements

The project will require the use of the following equipment:

Hot press

Optical microscope

Polishing equipment

Differential scanning calorimeter.

DMA

MTS and Instron mechanical testing machines.

X-CT equipment

# Project specific SMART KPIs

Two senior design projects on thermoplastics manufacturing.

Two journal publications.

Ten UAE Nationals trained.

# Progress reporting requirements

Monthly updates via the monthly progress reports.

The Abu Dhabi Economic Vision 2030, Section Three: Engines of Abu Dhabi’s Future Economic Growth. Published by Abu Dhabi Council for Economic Development, 2009.