## Test
|  |  |  | Prepared By: | Ref:
Client: | Khalifa University | Initials |  | AM | Test 11
Process: | ARIC Audit | Date |  | 2023-04-25
Period: | 1 Jan 2022 to 31 Dec 2022 | Internal Research
| Risk reference Number | WP_KU_A_11
Sr | Documents | Attributes
|  | A | B | C | Remarks | Document Referance
1 | Project Monitoring reports | a |  |  | Monthly progress reports are available from January to December 2022. | WP_1
2 | SMB Meetings |  | a |  | SMB meets on a quarterly basis and MoMS and presentations are available. One MoM was not signed by the SMB member. In-kind monitoring Clause 4.4 of Phase 2 agreement, KU is obligated to provide a financial contribution to the program, which includes 20% in-kind support amounting to AED 200,000 per year. The total in-kind contribution from KU for the period of 2019-2022 amounts to AED 600,000 as per agreement. we noted the absence of any reporting available regarding the actual in-kind contributions made by KU to the SMB in 2022, despite the monitoring of in-kind contributions being included in the monthly Financial Statements preparation process. SoW Statemen of Work was not approved by SMB Disbursement fo FUnds As per Section 4.7, “ If the SMB unanimously approves the draw-down of Center Funds, the SMB shall minute the following: a) The amount to be drawn down (Drawn Amount) and b) A description of the purpose for which the Drawn Amount is to be used. According to Clause "G" - Appendix - 1 of ARIC agreement, the role of the SMB is to "agree on the appropriate process to manage and disperse funds." However, it was observed that no documented process has been established to govern the disbursement of funds for ARIC. Additionally, there was no recorded approval in the meeting minutes for the drawdown of funds. Furthermore, during SMB meetings, only the budget versus actuals or net fund position balance was presented, and the specific amount of funds to be drawn down and its purpose was not documented | WP_2 WP_3 WP_4
Sampling Technique
Total Population |  | 1
Samples Selected |  | 1
Percentage |  | 100%
Tickmarks
A | 1- Ensure project monitoring reposts are created and shared with SMB
B | 2. Check whether SMB meets on a quarterly basis