## Test
[5 empty] | Prepared By: | Ref:
Client: | Khalifa University | Initials |  |  | AM | Test 3
Process: | ARIC Audit | Date |  |  | 2023-03-24
Period: | 1 Jan 2022 to 31 Dec 2022 | Internal Research
| Risk reference Number | WP_KU_A_3
Sr | Documents | Attributes
|  | A | B | C | D | Remarks | Document Referance
1 | Progress Reports | a |  |  |  | Monthly progress reports and SMB MoM are available. Center Assessment Reports comprehensive reports for external funded research centers are typically submitted to the Office of Research Services (ORS). ORS plays a vital role in facilitating research administration. During our review, it was observed that formal reporting from the ARIC to ORS was absent in 2022. Further, interim Reports / Center Assessment Reports were not developed and provided to ORS during 2022. Monthly Reports It was noted that following information was not captured consistently in the monthly reports which was stated in the Statement of Work for research projects. • Actual expenditure incurred on the project in comparison to the initial research project budget. • Progress made towards achieving the defined project-specific Key Performance Indicators (KPIs) up to date (Additive Manufacturing Projects and Graphene Based Sensors for Composite Applications) • Accomplishments of tasks in relation to the established timelines, including a Gantt chart representation (Additive Manufacturing Projects and Graphene Based Sensors for Composite Applications, robotic sorting of engine blades and robotic inspection of blades ) • Comparison between expected and actual allocation of manpower on the research projects. | WP_1
2 | Compliance |  | a |  |  | A new agreement has been signed for 2023-2027 in November 2022. Noted certain non compliances such as absence of minuted draw down of funds, one of the MoMs are not signed and Statement of Work are not approved by the SMB | WP_2
3 | Org chart |  |  | a |  | Organisation Chart approved by the SMB did not state the Deputy Director Position, which is a requirement as per the approved contract | WP_3
4 | Patents and publication |  |  |  | a | List of patents and publications were provided | WP_4
Sampling Technique
Total Population |  | 1
Samples Selected |  | 1
Percentage |  | 100%
Tickmarks
A | 1- Ensure there is progress monitoring and minutes are documented from SMB
B | 2 - Ensure compliance with the agreement
C | 3 - Obtain the Organisation structure for the ARIC center and make sure there is no shortage in staff and all approved positions are filled and org chart is approved by SMB
D | 4- Review process of patents and publication