## Test
|  |  |  | Prepared By: | Ref:
Client: | Khalifa University | Initials |  | AM | Test 5
Process: | ARIC Audit | Date |  | 2023-03-27
Period: | 1 Jan 2022 to 31 Dec 2022 | Internal Research
| Risk reference Number | WP_KU_A_5
Sr | Documents | Attributes
|  | A | B | C | Remarks | Document Referance
1 | Budget | a |  |  | The budget is created based on the future code for each research project. The budget for each project does not take into consideration the capex. Further the budgeted cost for each project against actuals is not clearly shown in the monthly progress report. “costs of participating individuals shall be included in the annual budgeting cycle to be approved by the SMB” and such costs “shall be treated as part of the operating cost of the Center, and not as in kind contribution by either Party”. It was noted that the budget (manpower and operating) were not estimated for 2022 as per the Statement of Work for Research Project (Graphene based Sensors for Composites Monitoring). However, the manpower costs were incurred for execution of research project. In addition, it was observed that the costs associated with the Core Lab Engineers were not included in the Project Costs for the Additive Manufacturing and Repair Project, despite it being continued in 2022 according to the approved Statement of Work from 2021 | WP_1
2 | Variations |  | a |  | t was observed that, out of the 5 projects scheduled for 2022, only 1 project was successfully completed according to the original plan. Further, the final technical report, as specified in the Statement of Work, was not prepared for the completed project, resulting in a delay of 5 months to prepare the final Technical Report. | WP_2
Sampling Technique
Total Population |  | 1
Samples Selected |  | 1
Percentage |  | 100%
Tickmarks
A | 1- Obtain and ensure that the budget is approved by the SMB. Also check if Statement of Work is available and cost appropriately.
B | 2- Check if there are any significant variations from the budget. Check whether the deliverables for Statement of Work is prepared and presented